## Slide 1: Project Management Topic 3
PROJECT MANAGEMENT TOOLS & TECHNIQUES
Sylvia Aarakit

## Slide 2: Outline
Needs assessment
Problem tree
Objective tree
Stakeholder matrix
Project schedules
Work Breakdown Structures
Activity plan
Resource plan
The Gantt Chart,
The Critical Path Method
Program Evaluation & Review Technique
Logical framework analysis

## Slide 3: 1. NEEDS ASSESSMENT

## Slide 4: 1. WHAT IS NEEDS ASSESSMENT?
This is a systematic process for determining needs, or “gaps” between current conditions and desired conditions or “wants”.
Looks at discrepancy between the current condition and wanted condition.
It is the basis for the development of a business case that builds the foundation for determining the project objectives and serve as inputs to a project charter.

## Slide 5
In Project Management, needs assessment is undertaken in the project initiation phase, before project work begins.
However, during the course of a project, there is need to revisit the needs assessment and decisions made previously to ensure they are still valid.
A needs assessment is a systematic process you’ll use to evaluate the non-negotiable requirements of your project. This could include knowledge, skills, systems, tools, and more.

## Slide 6: How to Conduct and Use Needs Assessment
Sometimes needs assessments aren’t included as part of the scoping stage of a project because those involved simply don’t know how to conduct a good one, or how important they really are.
Some find it hard to carry out a thorough and timely needs assessment due to difficulties associated with development work.
We recommend to form a team with different stakeholders to conduct a gap analysis as a starting point.
It is important to conduct a more formal and thorough needs assessment if you have the resources and time

## Slide 7
Needs assessment takes 3 steps i.e.
Perform a “Gap” Analysis – Compare the performance of your organization/people against the existing and target situation (also known as as-is and to-be analysis)

## Slide 8
2. Form Team and Priorities & Importance – Prioritize those needs in view of their importance to your organizational goals, realities, and constraints.
3. Integrate Prioritized Needs to Develop Business Case

## Slide 9: Why is a needs assessment important?
In your groups, discuss the reasons for undertaking needs assessment exercise in project.

## Slide 10: Outline
Needs assessment
Problem tree
Objective tree
Stakeholder matrix
Work Breakdown Structures
Project schedules
Activity plan
Resource plan
The Gantt Chart,
The Critical Path Method
Program Evaluation & Review Technique
Logical framework analysis

## Slide 11: 2. Problem Analysis

## Slide 12: What is a Problem Analysis in PI?
Problem analysis is central to many forms of project planning and is well developed among development agencies.
It identifies the negative aspects of an existing situation and deals with present issues rather than apparent, future or past issues.
It is often the first step that can help to find solutions by analyzing and mapping out the relationship of causes and effects around a main problem or issue.

## Slide 13: What is a Problem Analysis?
Problem analysis is the fourth step in Problem/Project Identification (PPI), which analyzes comprehensively and in depth key information obtained from situation analysis, feasibility study, and stakeholder analysis.
Situation Analysis
Feasibility Study
Stakeholder Analysis
Problem Analysis

## Slide 14: 3. Why Problem Analysis is important?
Problems can be broken down into manageable and definable chunks, which enables a clearer prioritization of factors and helps to focus on objectives; objective tree is the next step after problem tree.
Help to establish whether further information, evidence or resources are needed to make a stronger analysis of project’s problems.

## Slide 15: 2. Why Problem Analysis is important?
It is important in planning a project as it establishes the context in which a project is to occur. Understanding the context helps reveal the complexity of life and this is essential in planning a successful project.
The process of analysis often helps build a shared sense of understanding, purpose and action.

## Slide 16: Recommended tool for Problem Analysis : Problem Tree Analysis
A Problem Tree can be defined as a visualization of the problems in form of a diagram, or “hierarchy of problems” to help analyze and clarify cause–effect relationships, or as a tree that provides an overview of all the known causes and effects to an identified problem.

## Slide 17
Problem tree analysis examines the negative aspects of an existing situation and establishes the ‘cause and effect’ relationships between the identified problems.
Causes
Effects
Main Problem

## Slide 18: How to Create a Problem Tree?
Problem tree analysis is best carried out in a small focus group of about six to eight people using flip chart paper or an overhead transparency. It is important that factors can be added as the conversation progresses.

## Slide 19: How to Create a Problem Tree?
The first step is to discuss and agree the problem or issue to be analyzed. Do not worry if it seems like a broad topic because the problem tree will help break it down.
The problem or issue is written in the center of the flip chart and becomes the 'trunk' of the tree, or the 'focal problem’.
The wording does not need to be exact as the roots and branches will further define it, but it should describe an actual issue that everyone feels passionately about.

## Slide 20: How to Create a Problem Tree?
Next, the group identify the causes of the focal problem - these become the roots - and then identify the consequences, which become the branches.
These causes and consequences can be created on post-it notes or cards, perhaps individually or in pairs, so that they can be arranged in a cause-and-effect logic.

## Slide 21: How to Create a Problem Tree?
How to Create a Problem Tree?
Branches = Effects
Trunk = Main Problem
Roots = Causes
Causes
Effects
Main Problem

## Slide 22: How to Create a Problem Tree?
The heart of the exercise is the discussion, debate and dialogue that is generated as factors are arranged and re-arranged, often forming sub-dividing roots and branches.
Take time to allow people to explain their feelings and reasoning, and record related ideas and points that come up on separate flip chart paper under titles such as solutions, concerns and decisions.

## Slide 23: 4. Recommended tool for Problem Analysis: Problem Tree Analysis
How to Create a Problem Tree?
Discussion questions might include:
Do the problems represent the reality? Are the economic, political and socio-cultural dimensions to the problem considered?
What are the most serious consequences? Which are of most concern? What criteria are important to us in thinking about a way forward?

## Slide 24
Discussion questions might include:
Do the problems represent the reality? Are the economic, political and socio-cultural dimensions to the problem considered?
What are the most serious consequences? Which are of most concern? What criteria are important to us in thinking about a way forward?
Which causes are easiest / most difficult to address? What possible solutions or options might there be? Where could a policy change help address a cause or consequence, or create a solution?
What decisions have we made, and what actions have we agreed?
The Problem tree is closely linked to the Objectives Tree, another important tool in project formulation/preparation phase.

## Slide 25: Example of a Problem Tree Analysis
Very late in producing the annual report
Have great difficulty in presenting achievements of the organization
Annual report writing is not included in the annual work plan
Annual report writing is not prioritized
Team members have high work overload
Branch: effect
Trunk: main problem
Roots: causes

## Slide 26: Exercise
Group work to develop a Problem Tree
through the use of Problem Tree Analysis

## Slide 27: References
Brignani, N. (2013). Project Cycle Management for International Development Cooperation. Università degli Studi di Macerata.
EC. (2004). Aid Delivery Methods: Project Cycle Management Guidelines. European Commission.
Evaluation Toolbox. (2010). Problem Tree/Solution Tree Analysis. Evaluation Toolbox.
Hovland, I. (2005). Toolkit Successful Communication: a Toolkit for Researchers and Civil Society Organisations. Overseas Development Institute.
ODI. (2009). Planning tools: Problem Tree Analysis. Overseas Development Institute.
http://www.clipartbro.com/clipart-image/clip-art-tree-clipart-panda-free-images-clipart-61506

## Slide 28: 3. Objective analysis

## Slide 29: What is an Objective Tree Analysis
An Objective Tree is a Problem Tree that is transformed into a set of future solutions to the problems. Each negative problem is converted into an objective by rewriting it as a positive future statement.
Problem Statements | Objective Statements
Low agricultural production | High agricultural production
Lack of medical staff in rural areas | The number of medical staff in rural areas has increased

## Slide 30: What is an Objective Tree Analysis?
As the Objective Tree is transformed from the Problem Tree: the analysis of problems in the Problem Tree from Problem/Project Identification (PPI) is the basis and starting point for the Objective Tree analysis.
The positive statements are in fact objective statements that can be presented in a diagram showing a means – ends hierarchy, the objective tree.

## Slide 31: What is an Objective Tree Analysis?
The analysis of objective tree aims:
Provide a clear overview of the desired future situation once problems have been identified and reformulate into objectives;
Verify the hierarchy of objectives;
Illustrate the means-ends relationships in a diagram.

## Slide 32: What is an Objective Tree Analysis?
Problem Tree
Causes
Effects
Negative Statements
Means
Ends
Objective Tree
Positive Statements

## Slide 33: Reformulating Problem Statements into Objective Statements
Reformulating the problems into objectives has to be done very carefully.
If a statement makes no sense after rewording, write a replacement objective, or delete it, or leave the problem unchanged.
It is important to review the formulated objectives and the resulting objective tree.

## Slide 34
Problem statement: “lack of adequate rain levels” cannot be transformed into “adequate rain levels available” because it is an unrealistic objective. We cannot intervene into the natural phenomenon by predicting or hoping that there will be adequate rain.
This problem, however, could be rewritten as “irrigation system established and operational” which sounds more realistic and can be intervened.

## Slide 35
Problem statement: “river water quality is deteriorating” can be reformulated into “quality of river water is improved”.
Problem statement: “loss of confidence in public services” can be transformed into “people’s confidence in public services is restored”.
Problem statement: “public transportation is in bad condition” can be reformulated into “public transportation is kept in good condition”.

## Slide 36
Formulate the following problem statements into objective statements
Problem Statements
a. Farmers lack know-how in organic farming
b. Community members are not aware of HIV/AIDS prevention
c. High rate of alcohol consumption
d. High illiteracy rate of children from poor family background
e. Youth do not participate in community activities
f. Local community do not understand their roles and responsibilities in natural resources management
g. People do not save money for use in health care or emergency situation
h. Youth do not like to read
i. Community members do not want to buy health insurance

## Slide 37: Steps in Formulating an Objective Tree
Step 1
Reformulate all negative situations of the problems analysis into positive situations that are desirable and/or realistically achievable
Step 2
Step 3
If necessary: revise statements; add new objectives if these seem to be relevant and necessary to achieve the objective at the next higher level; or delete objectives which do not seem suitable or necessary
Check the means-ends relationships to ensure validity and completeness of the hierarchy; cause-effect relationships in the problem tree are turned into means-ends linkages in the objective tree

## Slide 38: Steps in Formulating an Objective Tree
The following diagram illustrates a transformation of a problem tree into an objective tree which uses “high staff turnover” as the main problem.
Problem Tree
High staff turnover
Delay in project delivery
High rate of recurring recruitment
Unstable team members
Unattractive salary package
Very high workload
Authoritarian managers
Reduced staff turnover
Better salary package
Reduced workload
Less Authoritarian managers
Project delivery meets the deadline
Low rate of recurring recruitment
Stable team members
Objective Tree

## Slide 39: Steps in Formulating an Objective Tree
Summary of Formulating an Objective Tree from a Problem Tree
Problem Tree |  | Objective Tree
Relationship: Causes-Effects | Negative statements are rewritten into positive statements | Relationship: Means-Ends
Branches: Effects |  | Ends: Objectives
Trunk: Main problem |  | Trunk: Purpose/Objective/Outcome
Roots: Causes |  | Means: Objectives

## Slide 40: Steps in Formulating an Objective Tree
Once complete, the objective tree provides a summary picture of the desired future situation, including the indicative means by which ends can be achieved.
As with the problem tree, the objective tree should provide a simplified but robust summary of reality. It is a tool to aid analysis and presentation of ideas/objectives.
Its main strength is that it keeps the analysis of potential project objectives firmly based on addressing a range of clearly identified priority problems.

## Slide 41: Examples of Objective Tree
(adapted from Norad (1989) in Groenendijk (2003))
An Example of Bus Accident
Problem Tree
Objective Tree
Main Problem  Purpose
Effects  Goals
Causes  Results
Causes  Activities
Effects  Goals

## Slide 42: Examples of Objective Tree
An Example of River Water Quality
(EC, 2004)
Problem Tree
Main Problem
Effects
Causes

## Slide 43: Examples of Objective Tree
An Example of River Water Quality
(EC, 2004)
Objective Tree
Purpose
Results
Goals/Overall Objectives
Activities

## Slide 44: Exercises
Group work on Objective Tree Analysis
Exercise #1: Farming and Agriculture
Exercise #2: Reproductive Health
Exercise #3: General Health Care
Exercise #4: Natural Resources Management
Exercise #5: Strengthening Community Network

## Slide 45: References
EC. (2004). Aid Delivery Methods: Project Cycle Management Guidelines. European Commission.
Groenendijk, L. (2003). Planning and Management Tools: a Reference Book. The International Institute for Go-Information Science and Earth Observation.
Johns Hopkins University. (2013). Module 4: Designing a Program. Johns Hopkins University.

## Slide 46: Outline
Needs assessment
Problem tree
Objective tree
Stakeholder matrix
Project schedules
Work Breakdown Structures
Activity plan
Resource plan
The Gantt Chart,
The Critical Path Method
Program Evaluation & Review Technique
Logical framework analysis

## Slide 47: 4. Stakeholder analysis

## Slide 48: Definition of key terms
A Stakeholder is any person or organization, that can be positively or negatively affected by, or cause an impact on the actions of a company/project or organization.
Stakeholders are persons, groups, institutions or things with interests/a stake in a project or programme.
They can influence or be influenced by the project activities.
Stakeholders are people & organisations that are actively involved in the project, or whose interests may be positively or negatively affected by the project (Larson & Gray, 2011)

## Slide 49: Categories of stakeholders
Primary stakeholders: Those ultimately affected either positively or negatively by the project.
  Double as the Internal Stakeholders (staff, direct beneficiary)
Secondary stakeholders: Intermediaries in the delivery process.
External stakeholders: Those affected by the project indirectly (development partners, gov’t).

## Slide 50: Composition of stakeholders
Stakeholders include:
Beneficiaries: Of the project-both targeted and untargeted. Beneficiaries form the User group, People who use the resources or service in an area.
Interest group: People who have an interest in, an opinion about, or who can affect the use of, a resource or service.
Decision makers: People who make project decisions
Those often excluded from the decision making process.

## Slide 51: Examples of stakeholders
Project team
Project managers
Top management
Administrative support
Functional managers
Funders of the project
Suppliers of equipments to the project.
Contractors
Government agencies
Other organizations
The target group/s and beneficiaries of the project/customers.

## Slide 52: Stakeholder analysis
Stakeholder analysis is a process of:
  identifying a project’s key stakeholders,
  their interests in the project and
  the ways those interests affect the risks or viability of the project.
It helps to identify the key persons or groups affected by a project and contributes to good project design and implementation.
This information is used to assess how the interests of those stakeholders should be addressed in the project plan

## Slide 53: Why stakeholder analysis?
Helps Project managers to assess the project environment. It can also help to:
  Draw out the interests of stakeholders in relation to the problems which the project is seeking to address
  Identify and resolve conflicts of interests between stakeholders which may influence the success of the project.
  Identify relations with stakeholders that can be built upon to improve success.
  Identify those who have rights, interests, resources, skills and abilities to take part in, or influence the course of the project.

## Slide 54: Why cont’s
  Assess the appropriate type of participation by different stakeholders at successive stages of the project.
  Identify the different expectations
  Form a basis for participatory planning and management and project sustainability strategy
  Improve the project’s understanding of the needs of those affected by the problem
  Identify potential winners and losers as a result of the project.
  Reduce or hopefully remove potential negative project impacts

## Slide 55: When to do a stakeholder analysis?
Always at the beginning of a project to draw out the main assumptions which are needed to make a project viable.
Also when projects are reviewed, or revised and when they are evaluated. i.e., throughout the project cycle to check that the needs of the stakeholders are being adequately addressed.

## Slide 56: Who should do the Stakeholder Analysis?
Anyone can carry out the stakeholder analysis but it is most usefully done by the project management team.
A group of stakeholders can also do the analysis.
A participatory approach will normally produce better results.
External persons can be involved but many stakeholders may have covert or hidden agendas.
In summary it should be done in a participatory manner by top management, Monitoring and Evaluation team, Planners and Implementers.

## Slide 57: The 5 concerns of the analysis
The analysis is concerned about the identification of:
  Need: What is needed from stakeholders for your success?
  Support: What support do you have from the stakeholders? Are they for you, against you or they are neutral?
  Impact: What is the effect of your success on your stakeholders?
  Power: What is the degree of power which the stakeholders have in relation to your ability to achieve your project goal?
  Influence: What is the degree of influence the stakeholders have in relation to your ability to achieve your project goal

## Slide 58: Framework of the analysis
Stakeholders | Problems What problems do they face? | Interests | Likely impact on the project | Priority
Primary |  | Determine e.g, High | Determine e.g., High | High priority
Secondary |  | Determine the level | Determine High or low | Possibly low

## Slide 59: Power/Influence and Stakeholders
Monitor | Maximum co-operation
Ignore | Monitor
Low
High
High
L
Influence
Powe
r

## Slide 60: Issues in stakeholder analysis
Actors: Those organizations and people who can take actions that influence the project.
Factors: Those that are not able to take actions but simply exist as part of the environment and can affect the project success (E.g. Inflation, cross cutting issues)

## Slide 61: Stakeholder Management Strategies
Stakeholder analysis may use two basic approaches:
  Buffering: How to protect the project from stakeholder influence/power.
  Bridging: How to cooperate and build interdependencies with key stakeholders

## Slide 62: Actions that can be used in Buffering
Insurance policies (Risk transfer)
Dealing with the Press cautiously/with care
Physical barriers and security systems, protecting the project assets
Signing agreements on matters agreed upon
Generating baseline information to guard against challenging the project success.
Setting up one group against the other to avoid joint action
Stakeholder against the other to avoid joint action.
Use of Celebrities to support your cause
Joint public appearances (All stakeholders)

## Slide 63: Actions that can be used in Bridging
Regular meetings with stakeholders
Consultations on major decisions
Networking/collaboration and partnering
Daily briefs to key stakeholders
Use of liaison officers/Public Relations Officers
Stakeholder participation in decision making throughout the whole project cycle. This is likely to result in:
  Improved effectiveness,
  Enhanced responsibility, and
  Improved sustainability.

## Slide 64: How to carry out a stakeholder analysis
Scan the project environment and identify potentially relevant actors and factors.
Screen actors and factors for:
  Dependency: How important are the actors and factors to the successful outcome of the project
  Risk: The likelihood of something going wrong
  Power: How much control or influence can be exercised over the actor or factor
3. Identify potential problem of actors and factors.
  Pay special attention to those with these characteristics:
    High dependency,
    High risks, and
    Power.

## Slide 65: How cont’s
4. Develop strategies to deal with problem actors or factors and act on them.
5. In general, your goal should be to reduce dependency and risks and increase your low power over key actors.
6. Repeat these steps throughout implementation. This type of context analysis should not be a one-time activity.
7. Conditions in the environment are always changing, so management strategies and contingencies will also need to change.

## Slide 66: Group Task
Come up with a stakeholder analysis for your identified project

## Slide 67: Template to use
Stakeholders basic characteristics | Problems What problems do they face? | Interests What do they want from the project? | Potential What might they bring to the project? | Linkages Are there any points of: Conflict? Cooperation? Dependency?
1. |  |  |  | 
2. |  |  |  | 
3. |  |  |  | 
4. |  |  |  | 

## Slide 68: Use this stakeholder matrix
Stakeholder & basic characteristics | Interests & how affected by the problem | Capacity & motivation to bring about change | Possible actions to address stakeholder interests

## Slide 69: Outline
Needs assessment
Problem tree
Objective tree
Stakeholder matrix
Project schedules
Work Breakdown Structures
Activity plan
Resource plan
The Gantt Chart,
The Critical Path Method
Program Evaluation & Review Technique
Logical framework analysis

## Slide 70: 6. Scheduling a Project/project schedules

## Slide 71: The Project Schedule
Scheduling project work is an essential element of project management
A project schedule is a timetable that shows the start and end date of all project tasks, how the tasks relate to each other and usually which team members or other resources are responsible for delivery. It is a dynamic document that is created during initial the planning stage. The approved project schedule acts as a baseline to work to, but it is maintained and updated throughout the project as things change.
While schedules are often thought of as planning and control tools, they are also critical communication tools for team members and stakeholders.

## Slide 72: Why Project Schedule?
Outlines the time needed for the required tasks
Establishes milestones to be met to complete the project on time
Allocates resources across tasks
Can be presented in various forms to suit different stakeholders
"​At its simplest, a project schedule is a list of the project tasks, and how long each will take. Typically, it also includes the resources required to complete the task which enables the resource cost of the task to be calculated. It’s a fundamental planning, control, and communication tool.“

## Slide 73: The three main types of project schedule
Master project schedule: a summary level schedule that highlights the key tasks and their estimated duration. This is useful as a high-level overview document for senior management or external stakeholders who don’t need the detail.
Milestone schedule: tracks major milestones but not every task or deliverable. It’s great for reporting status and helping teams see their progress at a glance.
​Detailed project schedule: this is a more operational level schedule that tracks every project activity. It’s designed for the project team and managers to keep track of every element of the project.

## Slide 74: Key contents of a project schedule
Typically, the project schedule should include the following information:
Deliverables: A description of the outputs created by the work done
Example: An app will be created that enables users to record their daily food intake
Task description: A description of the outcomes you want to produce
Example: One of the tasks is writing a user help guide containing FAQs
Task duration: The entire time taken to complete a task
Example: We estimate that the creation of the user help guide will take one person three working days

## Slide 75
Task start and end date: The dates the task will start and finish
Example: We have scheduled the user guide to be created between 4 May – 8 May
Task dependencies: Relationships between tasks
Example: We cannot commence building the app until after design approval
Project calendar: Defines the working and non-working times
Example: Weekends are not included as workdays in our schedule
Work packages: A group of related tasks within a project
Example: The app needs testing before it is launched. Testing is work package, and tasks within the work package include compatibility testing, interface testing, security testing, and beta testing

## Slide 76
Budgets: A detailed estimate of all costs expected during the project
Example: We have included $85,000 in the budget for the sub-contracted app designer
Resource availability: What resources you have available, when they are available, and any conditions of the availability
Example: Sam, our writer, is available for the first week of May to complete the user help guide
Schedule risk analysis: A technique to connect the risk profile of tasks to the schedule
Example: Considering possible staff absence, the task completion date is set at 9 May

## Slide 77: Benefits of effective project scheduling
The project schedule guides the project team as they deliver the project. It communicates progress to the team, management, and other stakeholders. Done well, it makes the entire project run more smoothly and helps you finish up on time and on budget. Data suggests only 30% of organisations are likely to deliver projects that are on time, but more effective scheduling will help.

## Slide 78
Contributes heavily to project success
Provides a clear roadmap to everyone at the beginning of the project
Manages stakeholder expectations
Monitors and communicates project progress
Ensures buy-in and accountability for tasks and deadlines
Lets the team know which tasks rely on others
Serves as an early warning system for potential project issues
Reserves your resources for when you need them

## Slide 79: Project scheduling process
The scheduling process includes ;
Identify activities
Identify activity dependencies
Estimate resources for activities
Allocate people to activities
Create project charts

## Slide 80: Project scheduling tools and techniques
Project managers use a range of tools and techniques to create, track and control their project schedules. These days, the tools are almost always digital. Here’s a brief description of some of the most common tools and techniques:
Work breakdown structure
Resource plan
Gantt charts
Critical Path analysis
PERT (programme Evaluation and Review Technique)

## Slide 81: Project scheduling tools
1. GANTT chart
The most common form of project schedule is the GANTT chart. It’s a horizontal bar chart that tracks activities over time. Depending on resource allocation and task relationships, the bars might be running in parallel or sequentially. It can be produced with differing levels of detail depending on the needs of the target audience.
2. Work breakdown structure
A graphic that details the deliverables by presenting key milestones within a hierarchy. It simplifies projects into smaller, more manageable groups. It also provides the necessary framework for detailed cost estimating and control along with providing guidance for schedule development and control.

## Slide 82
Schedule network analysis A graphic that depicts the interrelationships and timing of all project activities in chronological order. Critical path method The critical path method adds the times of all critical activities, taking into account dependencies, to determine the earliest time that the project can be completed. PERT charts The program evaluation and review technique uses a different method to calculate time compared to the critical path method. For each activity, the shortest time, the longest time, and the most likely time are estimated for each task. The time estimate for each task is the weighted average of the three estimates.

## Slide 83: Scheduling Simple Project
Examples might be coordinating delivery of resources for a workshop session, implementing a small marketing plan, or organizing a weeding , birth day party .
Notes: Simple projects involve only one or a few people over a short time. Typically, simple projects will have few tasks dependent on other tasks, and will be relatively simple and easy to coordinate. Examples might be coordinating delivery of resources for a workshop session, implementing a small marketing plan, or delivering a simple software enhancement.
Simple projects are often best run using simple Timetables and Action Plans. These should be prepared and negotiated with project staff to improve plans and get buy-in.
With simple projects, tools like Gantt Charts and Critical Path Diagrams may overcomplicate project scheduling and communication.
Appropriate Timetables and Action Plans are often sufficient to coordinate and implement simple projects.
It will often be enough to create a workback schedule, starting from the date by which the project must be completed, and listing all of the tasks in reverse order with due dates for each.

## Slide 84: 6. Work breakdown structure

## Slide 85: Managing projects in time and with in cost
Work Break down Structures(WBS)
A deliverable-oriented hierarchical decomposition of the work to be executed by the project team to accomplish the project objectives and create the required deliverables
It is used to define;
The what?
The who?
The how?
The when?
The how much?
Work is broken down into small tasks(WBS)

## Slide 86: Work Breakdown Structure
WBS = breaking down the project into a cohesive set of synchronous and specific tasks
Work Packages are individual project activities
1.0
1.2
1.3
1.4
1.2.1
1.2.2
1.2.3
1.3.1
1.3.2
1.2.3.1
1.2.3.2
Deliverables are major project components
Subdeliverables are supporting deliverables
The project is the overall project under development

## Slide 87: Work Breakdown Structure (WBS)
The WBS represents a logical decomposition of the work to be performed and focuses on how the product, service, or result is naturally subdivided. It is an outline of what work is to be performed.
LEVEL | ELEMENT DESCRIPTION
1 | Project
2 | Category
3 | Subcategory
4 | Sub-Subcategory
5 | Work Package

## Slide 88: Work Package

## Slide 89: Deliverables and Milestones
Deliverables
  Tangible, verifiable work products
  Reports, presentations, prototypes, etc.
Milestones
  Significant events or achievements
  Acceptance of deliverables or phase completion
  Cruxes (proof of concepts)
  Quality control
  Keeps team focused

## Slide 90: Benefits of WBS
Helps more accurately and specifically define and organise the scope of the total project.
Helps with assigning responsibilities, resource allocation, monitoring the project, and controlling the project.
The WBS makes the deliverables more precise and concrete so that the project team knows exactly what has to be accomplished within each deliverable.
Allows double check of all the deliverables' specifics with the stakeholders and make sure there is nothing missing or overlapping.

## Slide 91: Example of WBS: “Going for a Holiday”
holiday
travel
documents
passport
tickets
insurance
booking
choose
resort
confirm
brochures
household
cat!

## Slide 92: Example Work Breakdown Schedule

## Slide 93: The WBS Should Follow the Work Package Concept

## Slide 94: Developing the WBS
The WBS Should Be Deliverable-Oriented
The WBS Should Support the Project's MOV
  Ensure WBS allows for the delivery of all the project’s deliverables as defined in project scope
  100 percent rule
The Level of Detail Should Support Planning and Control
Developing the WBS Should Involve the People Who Will Be Doing the Work
Learning Cycles and Lessons Learned Can Support the Development of a WBS

## Slide 97: Responsibility Matrix
Intersection of WBS and organization structure
Rows = persons or functional positions
Columns = work tasks or packages for which each personnel is responsible
Useful for monitoring and control

## Slide 99: Estimation Techniques of WBS
Guesstimating
Delphi Technique
Top-Down
Bottom Up
Analogous Estimates (Past experiences)
Parametric Modeling (Statistical)

## Slide 100
Guesstimating
  Based on feeling and not facts
  Not a good method for estimating but often used by inexperienced project managers
Delphi Technique
  Involves multiple, anonymous experts
  Each expert makes an estimate
  Estimates compared
    If close, can be averaged
    Another iteration until consensus is reached

## Slide 101
Top-Down Estimating
    Top and middle managers determine overall project schedule and/or cost.
    Lower level managers are expected to breakdown schedule/budget estimates into specific activities (WBS).
Bottom-Up Estimating
  Most common form of project estimation
  Starts with people who will be doing the work
  Schedules & budgets are the aggregate of detailed activities & costs
Analogous estimating
  Use information from previous, similar projects as a basis for estimation
Parametric Modeling
  Use project characteristics (parameters) in a mathematical model to estimate

## Slide 102: The advantages of the WBS
Breaks the project down into pieces and then to arrange the pieces in a logical way.
This helps to:
indicate how schedules and costs will be managed
give visibility to important or risky work efforts
allow mapping of requirements and deliverables
foster ownership
provide performance standards
make sense to all role players and stake holders

## Slide 103: Outline
Needs assessment
Problem tree
Objective tree
Stakeholder matrix
Project schedules
Work Breakdown Structures
Activity plan
Resource plan
The Gantt Chart,
The Critical Path Method
Program Evaluation & Review Technique
Logical framework analysis

## Slide 104: ACTIVITY PLAN
The purpose of this activity is to come up with a list of all activities of the project with their timelines, and to also prepare a work break-down structure (WBS) for the project.

## Slide 105: Activity plan

## Slide 106: Resource Plan
A resource plan identifies the physical resources required to complete the project.
This consists of labor, equipment, and materials required which for convenience are summarized in a schedule outlining when each of the resources is required and the activities that will require the resources.
A resource plan is developed typically towards the end of the planning stage after the Work Breakdowns (WBS) have been identified

## Slide 107: Resource plan
Drawing a resource Plan:
List the types of resources to be utilized, number of resources and purpose
Identify when they will be needed leading to production of resource schedule
Allocate the resources to the activities-resources usage table

## Slide 108: Gantt Chart
Gantt Chart -A bar chart that graphically represents the schedule of project activities.
The Gantt chart is a graphical presentation of a planned course of action and provides a means for comparing actual performance with planned performance.
On the Gantt chart after drawing the critical path, you also draw the other activities that are not critical but showing the extra time they have using dotted lines.
Typically show the task name and start and finish date for each task
They will have to change with time but are useful starting points

## Slide 109: Examples of GANTT charts
GANTT charts are created in packages such as Microsoft Project
But GANTT charts can also be created in Excel or in MS Word

## Slide 110: The advantages of the Gantt chart are
Time is explicit (and linear)
All tasks visible in relationship to others deadlines are shown
Project status at intermediate times is shown
can show progress by “filling in” task boxes
The chart makes visualization of schedule clearer.
Estimated time of each activity becomes conspicuous.
The project completion time is graphically illustrated

## Slide 111: To draw up a Gantt diagram, follow these steps:
1. List all activities in the plan
For each task, show the earliest start date, estimated length of time it will take, and whether it is parallel or sequential. If tasks are sequential, show which stages they depend on.
2. Head up graph paper with the days or weeks through to task completion
3. Plot the tasks onto the graph paper
Plot each task on the graph paper, showing it starting on the earliest possible date. Draw it as a bar, with the length of the bar being the length of the task.

## Slide 112
4. Schedule Activities
Now take the draft Gantt Chart, and use it to schedule actions. Schedule them in such a way that sequential actions are carried out in the required sequence. Ensure that dependent activities do not start until the activities they depend on have been completed.
5. Presenting the Analysis
The final stage in this process is to prepare a final version of the Gantt Chart. This should
combine the draft analysis with your scheduling and analysis of resources. This chart will show when you anticipate that jobs should start and finish.

## Slide 113: Critical Path Analysis & PERT Charts

## Slide 114: Critical Path Analysis and PERT Charts
Critical Path Analysis and PERT are powerful tools that help you to schedule and manage complex projects.
They act as the basis both for preparation of a schedule, and of resource planning

## Slide 115: Critical Path Analysis
This technique is a modelling process used to predict project duration by analysing which sequence of activities has the least amount of scheduling flexibility
Flexibility known as ‘slack’ or ‘float’
Latest finish – earliest start – duration = float
If float equals zero, this item is on the critical path

## Slide 116
Example: Doing your assignment
When is the earliest start date?
When is the latest finish date?
How long is the duration?
How much float do you have?
Is it on the critical path for achieving your degree?

## Slide 117: Components of CPA
Considers the path we can take to achieve the required target. It involve determining;
Early Start Time (the earliest time the activity can be started assuming all other proceeding activities start as early as possible)
Early Finish Times (the earliest times the activity can be completed)
Late Start Times (the latest time an activity can start without delaying the project) and
Late Finish Times (the latest time the activity can be completed and not affect/delay the project.

## Slide 118
Activity: An element of the project that requires time.
Merge activity: This is activity that has more than one activity immediately preceding it(more than one dependency arrow flowing to it)
Parallel Activity: activities that take place at the same time, if the manager wishes.
Path: A sequence of connected, dependent activities.
Event: Represents a point in time when an activity is started or completed.
Burst activity: refers to an activity which has more than one activity immediately following it (more than one dependency arrow flowing form it)

## Slide 119
Slack /float. The amount of time a task can be delayed without delaying the entire project.(Late start time –Early Start time)
Total float .The cumulative delay of all interrelated activities and Free float i.e an individual task float.
Critical tasks/activities. Those tasks delay of which will affect the entire project duration. They do not have a float or have zero float because they can not be delayed if the project is to be completed on schedule.
Critical path – is the quickest/shortest route that the project can take to be accomplished with minimal resources. It has zero slack time or delay.

## Slide 120: Benefits of CPA
CPA formally identifies tasks which must be completed on time for the whole project to be completed on time, and also identifies which tasks can be delayed for a while if resources need to be reallocated to catch up on missed tasks.
CPA helps you to identify the minimum length of time needed to complete a project.

## Slide 121: Benefits of CPA
Helps calculate minimum length of time in which a project can be completed and which activities should be prioritised to complete by that date
Helps you focus on the critical activities
Based on an assumption that some activities are dependent on other activities being completed first (sequential).
If activities are not dependent, then they can be done at any time or ‘parallel’ to other tasks.
The disadvantage of CPA is that the relation of tasks to time is not as immediately obvious as with Gantt Charts. This can make them more difficult to understand for someone who is not familiar with the technique.

## Slide 122: Drawing a Critical Path Analysis Chart
1. List all activities in the plan
2. Plot the activities as a circle and arrow diagram
For each activity, show the earliest start date, estimated length of time it will take, and whether it is parallel or sequential. If tasks are sequential, show which stage they depend on.

## Slide 123: Drawing a Critical Path Analysis Chart
2. Plot the activities as a circle and arrow diagram
Critical Path Analyses are presented using circle and arrow diagrams.
In these, circles show events within the project, such as the start and finish of tasks. Circles are normally numbered to allow you to identify them

## Slide 124: Drawing a Critical Path Analysis Chart
Figure 2: Simple Circle and Arrow Diagram

## Slide 125: Critical Path Analysis and PERT Charts
Critical Path Analysis is an effective and powerful method of assessing:
What tasks must be carried out
Where parallel activity can be performed
The shortest time in which you can complete a project
Resources needed to execute a project
The sequence of activities, scheduling and timings involved
Task priorities
The most efficient way of shortening time on urgent projects.

## Slide 126: Programme Evaluation and Review Technique (PERT) chart
Network techniques
Used for displaying project schedules that depict tasks and the dependencies between tasks.

## Slide 127: Programme evaluation and review technique (PERT) chart
PERT is useful for determining how much time a project needs for completion
Each activity is assigned a best, worst, and most probable completion time estimate, from which an average can be calculated
This average is then used to find the critical path.

## Slide 128: Programme Evaluation and Review Technique (PERT) chart
Time you
estimate the activity
will take

## Slide 129: Logical Framework Approach-LFA

## Slide 130: Logical framework Approach
Is an analytical, presentational and mgt tool.
It can help to;
Analyze the existing situation during project preparation.
Establish a logical hierarchy of means by which objectives will be achieved.
Identify the potential risks to achieving the objective, and to sustain outcomes
Establish how outputs and outcomes might be monitored and evaluated.
Present a summary of the project in a standard format

## Slide 131: Why cont’d
Monitor and review projects during implementation.
Planners can test the design of a proposed project to ensure its relevance, feasibility and sustainability.
Helps to think through all the factors that should be considered for planning a successful project.
Its a useful tool for planning more complicated projects.
A key management tool during implementation, monitoring and evaluation

## Slide 132: When to use the LFA?
Throughout the Project Management Cycle when;
Identifying & assessing activities that fit within the scope of programs.
Preparing the project design in a systematic & Logical way.
Appraising project designs.
Implementing approved projects; and
Monitoring, review and evaluating project progress & performance.

## Slide 133: Who should be involved?
It should be approached in team work;
Project manager, team members and key stakeholders involvement is key.

## Slide 134: The logical framework matrix
Gives a summary of;
What the project intends to do;
How;
What the key assumptions are; and
How outputs and outcomes will be monitored and evaluated.

## Slide 135: Log frame matrix structure
Project Elements | Objectively Verifiable Indicators (OVI) | Means of Verification (MOV) | Assumptions
Project Goal |  |  | 
Project Purpose |  |  | 
Results |  |  | 
Activities |  |  | 

## Slide 136: How to design a log frame?
The logical framework requires that you:
write down the planned activities in a certain order that helps you to check whether one step will lead to the next.
note any assumptions that you are making, and examine whether or not they are true.
identify indicators of progress.

## Slide 137: The idea is to come out with a logical relationship between the 5 Project elements.
If we have the appropriate ……………….………………INPUTS
We can perform all………………………………………ACTIVITIES
Which are needed to deliver our…………….………RESULTS
If we achieve all results this will make it possible to achieve our……………………………………………PROJEC PURPOSE
Which contribute to the achievement of………………………………………………………..DEVELOPMEN GOAL

## Slide 138: Structure Explained- GOAL
  Goal is a strategic or programmatic rationale for the project
  It describes achievement at the National, sector, programme or strategic level.
  The goal describes what the purpose of this project when combined with others will achieve e.g. if farm production is increased (purpose), then farm household income will be increased (goal)
  Goals are derived from organisation’s Strategic plans and Partner purposes.

## Slide 139: Project Purpose:
  The purpose describes the desired effect we hope the project will have.
  The purpose is the justification for the project, why the project is being undertaken.
  It is the how the target beneficiary behavior is expected to change because of the project Outputs.
  It describes the response of the client (target beneficiary) to the project.
  As a rule of thumb a project should have only one Purpose.

## Slide 140: Project Outputs:
  The outputs describe the project deliverables, the goods and services for which the project implementers are accountable.
  These are concrete, often tangible deliverables envisaged in order to achieve project purpose.
  Each output is envisaged as a vital means to achieve the purpose.
  All outputs are defined and feasible within the resources available.

## Slide 141: Project Activities:
  The activities describe how the team will accomplish each of the Outputs (action strategy)
  They reflect the starting point for the implementation planning process.
  Activity clusters (WBS) are used preferably only 3-7 essential Activities necessary to produce each Output.

## Slide 142: Checklist on Project Activities:
  Ensure that all activities contribute directly to each Output.
  The Activities define any actions required for gathering the means of verifying the elements described in the M&E system.
  Only those activities to be performed by the project are included.
  Activities are stated in terms of actions being undertaken that as completed action the way outputs are stated.

## Slide 143: Checklist on Project Activities Cont:
  For the purpose of project matrix (LFA) the activities are a brief summary of 3-7 actions to each output and to provide the basis for a WBS analysis or a more elaborate Activity Chart, Bar Chart or Gantt Chart.
  Ensure activities are appropriate to the situation in the parent organization or beneficiary community (including host country) in terms of institutions, technology, culture etc.
  Activities should include the basic actions of the project management team:
  E.g. Project Launch (1wk), Stakeholder Conference/Workshop (2days), M&E System Design Conference (2days), Quarterly Review meeting (1day), Annual Assessment Workshop for all stakeholders (4days)

## Slide 144: Inputs
The resources needed to conduct the activities.
Resources refer to personnel, raw materials, capabilities, fincances e.t.c.

## Slide 145: Objectively Verifiable Indicators (OVIs)
These describe the basis of measuring how well the objectives and results have been achieved.
Indicators refer to the information we need to help us determine progress towards meeting stated project objectives. QQT
The indicators at each level are different & measure change at that level
The indicators define the deliverables for which the contractor is accountable
Indicate how to recognize success/failure at each level
  Reduced mortality rate from 85% to 55% by 2014
  Number of Patients attended to per day;

## Slide 146: Objectively Verifiable Indicators (OVIs)
These describe the basis of measuring how well the objectives and results have been achieved.
Indicators;
state how the performance standards to be reached will be measured.
provide the information needed to help us determine progress towards meeting stated project objectives.
Set target for the project to achieve.
Can be direct or indirect.

## Slide 147: Means of Verification(MOV)
The MOV refers to how and where one can check that an objective has been achieved at the intended performance level.
In other words, means of verification are data sources.
The sources of information on achievement of objectives need to be agreed at the planning stage, i.e. what information
is needed,
In what form,
the frequency and
who should provide it
to ensure that there are ways of verifying success.

## Slide 148: Project Assumptions
Assumptions are the important and relevant factors:
Which are out of the control of the project; but
Which must exist or take place if the project is to be successful.
An assumption is a positive statement of a condition that must be met in order for project objectives to be met; while

## Slide 149: Risks and precondition
A risk is a negative statement of what might prevent objectives being achieved.
Preconditions are conditions that must be met before a project can commence e.g. policy

## Slide 150: Diagonal Logic

## Slide 151: Structure Of The Log Frame
Project Description |  | Objectively verifiable indicators of achievement | Sources and means of Verification | Assumptions
GOAL | What is the overall broader impact to which the action will contribute? | What are the key indicators related to the overall goal? | What are the sources of information for these indicators? | What are the external factors necessary to sustain objectives in the long term?
PURPOSE | What is the immediate development outcome at the end of the project? | Which indicators clearly show that the objective of the action has been achieved? | What are the sources of information that exist or can be collected? What are the methods required to get this information? | Which factors and conditions are necessary to achieve that objective? (external conditions)

## Slide 152
OUTPUTS | What are the specifically deliverable results envisaged to achieve the specific objectives? | What are the indicators to measure whether and to what extent the action achieves the expected results? | What are the sources of information for these indicators? | What external conditions must be met to obtain the expected results on schedule?
ACTIVITIES | What are the key activities to be carried out and in what sequence in order to produce the expected results? | Means: | What are the | What pre conditions are required before the action starts?
 |  | What are the means required to implement these activities, e.g. personnel, equipment, supplies, etc. | Sources of information about action progress? | 
 |  |  | Costs | 
 |  |  | What are the action costs? |