## Slide 1: Project Identification & Design
By:
Francis Kenneth Kimbugwe

## Slide 2: Project Identification and Design
During the project identification and design phase, project teams and stakeholders work together collaboratively and systematically to:
  identify project ideas
  collect assessment data
  analyze the project assessment data
  develop the project logic or design.

## Slide 3: Project identification
Looks at the issue that makes the project necessary.
This is done through a “needs assessment”.
Needs identification seeks the real needs to be satisfied. You have to understand the situation before intervention.
This stage is critical for the success of the rest of the project
It is some times called situation analysis stage.
Project identification involves the following:
Identifying and assessment of needs
Analyse the Stakeholders.
Analyse the problem,
Identification of objective and;
Selection of the strategy.

## Slide 4: Questions to help in identifying project ideas
Where do ideas come from?
Who identified the needs and opportunities?
What evidence is required to support needs?

## Slide 5: Assessment of needs
Needs assessment looks at assessing what community/organisational needs are, whom they affect.
Jonathan Bradshaw (1972) work.
Four methods of defining and measuring needs:
Felt needs.
  Verbalized directly or indirectly by the concerned person or her family or community.
  Defined by the individual’s or the community’s own perception of need and any discrepancy between their situation and what they believe it ought to be.

## Slide 6: Four methods of defining and measuring needs
Expressed needs.
  Defined as a felt need that has become a demand from an individual or a community.
  Expressed needs refer to what can be inferred about community needs by observation of the community's use of services .
Normative needs/assessed:
  Defined by the observations of experts, professionals and consultants who implicitly or explicitly compare the current situation to a set of professional or expert standards.
Comparative needs.
  Defined by comparing the differences in people’s access to resources.

## Slide 7: Collecting assessment data
(1) Confirm that the idea; (2) to suggest adjustment to the idea before moving forward; (3) to point to a more viable project idea.
Forms of assessment of project ideas:
Socio-economic information on the target community or group or organisation and other stakeholders.
Gathering data on the current state of livelihood security, market share, employee capabilities.
Canvasing target populations about their current knowledge, behavior and attitudes.
Mapping the geography and bio-physical assets of the intervention area.
Identifying the policies that might impact (+vely or –vely) a potential project intervention.

## Slide 8: Course work Assignment Take Home
Question :
Identify a project idea and take it through the assessment, analysis, and design and action planning to come up a project (Plan) operations plan.
a. Identify a project idea or opportunity and describe its source(s), how you were able to identified it, and the evidence to support the need (s).

## Slide 9: Analysis Phase
Objectives of analysis:
Examine the causes and effects of the problems or issues.
Involves reflection and examining the ways in which these problems or issues are linked to each other.
Operation processes:
Stakeholder analysis – power-interest gride for stakeholder priortisation/stakeholder matrix.
Problem analysis – Problem tree/pyramid; Doctor-Patient; Participatory diagnosis; expert method; Ishikawa. Fish born method. Core/major problem or issues; effects; underlying issues and root causes.
Objectives analysis
Strategy analysis and selection

## Slide 10: Stakeholder analysis:
Stakeholder Analysis is defined as a process of systematically gathering and analysing qualitative information to determine whose interests should be taken into account when developing and or implementing a policy or program.
Stakeholder analysis is a process of identifying a project’s key stakeholders, their interests in the project and the ways those interests affect the risks or viability of the project.
A Stakeholder is any person or organization, that can be positively or negatively affected by, or cause an impact on the actions of a company/project or organization.

## Slide 11: Examples of stakeholders
Project team
Project managers
Top management
Administrative support
Functional managers
Funders of the project
Suppliers of equipments to the project.
Contractors
Government agencies
Other organizations
The target group/s and beneficiaries of the project/customers.

## Slide 12: Categories of stakeholders.
Stakeholders can be categorized as:
Primary / internal stakeholders: Those ultimately affected either positively or negatively by the project. E.g. staff, direct beneficiary.
Secondary stakeholders: Intermediaries in the delivery process.
External stakeholders: Those affected by the project indirectly e.g. development partners, gov’t, Suppliers of equipments.

## Slide 13: Benefits of stakeholder analysis
We are able to identify who has an interest in the success or failure of the project.
Draw out the interests of stakeholders in relation to the problems which the project is seeking to address.
Identify and resolve conflicts of interests between stakeholders which may influence the success of the project.
Assess the appropriate type of participation by different stakeholders at successive stages of the project.
Form a basis for participatory planning and management and project sustainability strategy

## Slide 14: Benefits Cont’d
Improve the project’s understanding of the needs of those affected by the problem
Identify potential winners and losers as a result of the project.
Identify those who have rights, interests, resources, skills and abilities to take part in, or influence the course of the project.
We better understand the social and political issues which the project planners must take into account.
Gaining support from powerful stakeholder can help to win more resources.
Allows early and frequent communication with stake holders which ensures full understanding of what is being done to understand the benefits of the project.

## Slide 15: Steps stakeholder analysis
Identify who your stakeholders are & classify them i.e. List all the possible participants or stakeholders in a potential project.
Work out their power, influence & interest, so you know who you should focus on.- look for Actors and Factors.
Formulate methods of bringing them on board. i.e. strategies (Buffering or bridging).

## Slide 16: Tool: Power- Interest Grid for Stakeholder Priorisitsation
A
B
D
C

## Slide 17: Stakeholder Matrix
Stakeholders basic characteristics | Problems What problems do they face? | Interests What do they want from the project? | Potential/capacity and motivation to bring about change. What might they bring to the project? | Possible actions to address stakeholder interest/strategies.
!. Stakeholder 1: |  |  |  | 1. Buffering 2. Bridging
2. Stakeholder 2: |  |  |  | 
3. Stakeholder 3: |  |  |  | 

## Slide 18
b. Conduct a stakeholders analysis for your project using a stakeholder matrix.

## Slide 19: Problem Analysis
A problem analysis looks at the prevailing situation to get the right image of the reality.
A problem justifies the existence of a project.
A problem well understood is a Problem Half-Solved
A problem tree is one of the most widely used tools used to conduct problem analysis.
A tool used is a problem tree illustrating the various problems.

## Slide 20: Steps in Problem Analysis
Define the framework and subject of the analysis.
Analyze interested parties/stakes/stake holder analysis.
Analyse the problematic situation/problem tree.
Priotise the problems in order of importance and rank them.
Select the one with the highest cause effect relationship ( use the concept of opportunity cost to make a choice).

## Slide 21
Cause –effect principle
Core problem or issue

## Slide 22: Approaches to problem analysis
The Fishbone diagram.
Doctor-Patient Method
The expert method
Participatory Diagnosis
The pyramid/problem tree method

## Slide 23
C. Conduct a problem analysis for your project a problem tree method.

## Slide 24: Objectives Analysis
It looks at the solution to the problem & the effect of the solution.
Its about changing undesirable conditions (the problem) into desirable condititions (the objectives).
One of the simplest approaches to objectives analysis is the objectives tree. An “objective tree” describes the range of potential improvements relating to people’s lives.
Benefits
Describe the situation that should prevail after the problem has been solved.
Identify & set the objectives in the order of importance.
In understanding the impracticable and feasible situations.

## Slide 25
C. Come an objective analysis for your project an objectives tree method.

## Slide 26: Analysis of strategy
Strategy is the direction and scope of organisation based on the advantages, resources, environment & stakeholders in the project.
Identify possible strategy so as to attain the objectives.
Three questions to consider are:
Which elements of the objectives tree will be included in the project intervention?
Which elements will not be included in the scope of the project?
What are the criteria which will be used to make these decisions?

## Slide 27: Factors to consider when selecting the strategy.
Priority of the stakeholder
Probability of success
Time frame
External program considerations
Appropriateness
Institutional capacity
Budget limitations.
Resource availability/Budget limitations.
Financial/economic feasibility
Technical feasibility and sustainability
Internal program considerations
Portfolio considerations

## Slide 28: Strategy analysis Matrix
option criteria | 1 | 2 | 3 | 4
Cost effectiveness (Budget issues) |  |  |  | 
The number of people it will reach |  |  |  | 
Is it environmental sustainable |  |  |  | 
How long will it take to be achieved (Time frame ) |  |  |  | 

## Slide 29
d. Describe your project strategy or approach for responding to the need or project idea.

## Slide 30
end