## Slide 1: Monitoring and Evaluation methods and tools.
Performance Indicators
The Logical Framework approach
Theory-based evaluation
Formal surveys
Rapid appraisal methods
Participatory methods
Public expenditure tracking surveys
Cost-benefit and Cost-effectiveness analysis
Impact evaluation

## Slide 2: Performance Indicators
What are they?
Performance indicators are measures of inputs, processes, outputs, outcomes, and impacts for development projects, programs, or strategies.
When supported with sound data collection—perhaps involving formal surveys—analysis and reporting, indicators enable managers to track progress, demonstrate results, and take corrective action to improve service delivery.
Participation of key stakeholders in defining indicators is important because they are then more likely to understand and use indicators for management decision-making.

## Slide 3: What can we use them for?
■ Setting performance targets and assessing progress toward achieving them.
■ Identifying problems via an early warning system to allow corrective action to be taken.
■ Indicating whether an in-depth evaluation or review is needed.

## Slide 4: Advantages
■ Effective means to measure progress toward objectives.
■ Facilitates benchmarking comparisons between different organizational units, districts, and over time.
DISADVANTAGES:
■ Poorly defined indicators are not good measures of success.
■ Tendency to define too many indicators, or those without accessible data sources, making system costly, impractical, and likely to be underutilized.
■ Often a trade-off between picking the optimal or desired indicators and having to accept the indicators which can be measured using existing data.

## Slide 5: The Logical Framework Approach
What is it?
The logical framework helps to clarify objectives of any project, program, or policy.
It aids in the identification of the expected causal links the “program logic” in the following results chain: inputs, processes, outputs (including coverage or “reach” across beneficiary groups), outcomes, and impact.
It leads to the identification of performance indicators at each stage in this chain, as well as risks which might impede the attainment of the objectives.
The Log Frame is also a vehicle for engaging partners in clarifying objectives and designing activities.

## Slide 6
During implementation the Log Frame serves as a useful tool to review progress and take corrective action.
What can we use it for?
■ Improving quality of project and program designs—by requiring the specification of clear objectives, the use of performance indicators, and assessment of risks.
■ Summarizing design of complex activities.
■ Assisting the preparation of detailed operational plans.
■ Providing objective basis for activity review, monitoring, and evaluation.

## Slide 7
ADVANTAGES:
Ensures that decision-makers ask fundamental questions and analyze assumptions and risks.
Engages stakeholders in the planning and monitoring process.
When used dynamically, it is an effective management tool to guide implementation, monitoring and evaluation.
DISADVANTAGES:
If managed rigidly, stifles creativity and innovation.
If not updated during implementation, it can be a static tool that does not reflect changing conditions.
Training and follow-up are often required.

## Slide 8: Theory-Based Evaluation
What is it?
Theory-based evaluation has similarities to the Log Frame approach but allows a much more in-depth understanding of the workings of a program or activity the “program theory” or “program logic.”
In particular, it need not assume simple linear cause and effect relationships.
For example, the success of a government program to improve literacy levels by increasing the number of teachers might depend on a large number of factors.
  These include, among others, availability of classrooms and textbooks, the likely reactions of parents, school principals and schoolchildren, the skills and morale of teachers, etc

## Slide 9
By mapping out the determining or causal factors judged important for success, and how they might interact, it can then be decided which steps should be monitored as the program develops, to see how well they are in fact borne out.
This allows the critical success factors to be identified.
And where the data show these factors have not been achieved, a reasonable conclusion is that the program is less likely to be successful in achieving its objectives.

## Slide 10: What can we use it for?
Mapping design of complex activities.
Improving planning and management.
ADVANTAGES:
Provides early feedback about what is or is not working, and why.
Allows early correction of problems as soon as they emerge.
Assists identification of unintended side-effects of the program.
Helps in prioritizing which issues to investigate in greater depth, perhaps using more focused data collection or more sophisticated M&E techniques.
Provides basis to assess the likely impacts of programs.

## Slide 11
DISADVANTAGES:
■ Can easily become overly complex if the scale of activities is large or if an exhaustive list of factors and assumptions is assembled.
■ Stakeholders might disagree about which determining factors they judge important, which can be time-consuming to address.

## Slide 12: Formal Surveys
What are they?
Formal surveys can be used to collect standardized information from a carefully selected sample of people or households. Surveys often collect comparable information for a relatively large number of people in particular target groups.

## Slide 13
What can we use them for?
■ Providing baseline data against which the performance of the strategy, program, or project can be compared.
■ Comparing different groups at a given point in time.
■ Comparing changes over time in the same group.
■ Comparing actual conditions with the targets established in a program or project design.
■ Describing conditions in a particular community or group.
■ Providing a key input to a formal evaluation of the impact of a program or project.
■ Assessing levels of poverty as basis for preparation of poverty reduction strategies.

## Slide 14
ADVANTAGES:
■ Findings from the sample of people interviewed can be applied to the wider target group or the population as a whole.
■ Quantitative estimates can be made for the size and distribution of impacts.
DISADVANTAGES:
■ With the exception of CWIQ, results are often not available for a long period of time.
■ The processing and analysis of data can be a major bottleneck for the larger surveys even where computers are available.
■ LSMS and household surveys are expensive and time-consuming.
■ Many kinds of information are difficult to obtain through formal interviews.

## Slide 15: Some Types of Survey
Multi-Topic Household Survey (also known as Living Standards Measurement Survey-LSMS)
This is a multi subject integrated survey that provides a means to gather data on a number of aspects of living standards to inform policy. These surveys cover: spending, household composition, education, health, employment, fertility, nutrition, savings, agricultural activities, other sources of income.
Single-topic household surveys cover a narrower range of issues in more depth. Core Welfare Indicators Questionnaire (CWIQ)
This is a household survey that measures changes in social indicators for different population groups specifically indicators of access, utilization, and satisfaction with social and economic services. It is a quick and effective tool for improving activity design, targeting services to the poor and, when repeated annually, for monitoring activity performance. Preliminary results can be obtained within 30 days of the CWIQ survey.
Client Satisfaction (or Service Delivery)
Survey is used to assess the performance of government services based on client experience. The surveys shed light on the constraints clients face in accessing public services, their views about the quality and adequacy of services, and the responsiveness of government officials. These surveys are usually conducted by a government ministry or agency.
Citizen Report Cards
These are conducted by NGOs and think-tanks in several countries. Similar to service delivery surveys, they have also investigated the extent of corruption encountered by ordinary citizens. A notable feature has been the widespread publication of the findings.

## Slide 16: Rapid Appraisal Methods
What are they?
Rapid appraisal methods are quick, low-cost ways to gather the views and feedback of beneficiaries and other stakeholders, in order to respond to decision-makers’ needs for information.

## Slide 17: What can we use them for?
■ Providing rapid information for management decision-making, especially at the project or program level.
■ Providing qualitative understanding of complex socioeconomic changes, highly interactive social situations, or people’s values, motivations, and reactions.
■ Providing context and interpretation for quantitative data collected by more formal methods.

## Slide 18
ADVANTAGES:
■ Low cost.
■ Can be conducted quickly.
■ Provides flexibility to explore new ideas.
DISADVANTAGES:
■ Findings usually relate to specific communities or localities thus difficult to generalize from findings.
■ Less valid, reliable, and credible than formal surveys.

## Slide 19: Rapid Appraisal Methods
Key informant interview: These are a series of open-ended questions posed to individuals selected for their knowledge and experience in a topic of interest. Interviews are qualitative, in-depth, and semi-structured. They rely on interview guides that list topics or questions.
Focus group discussion: These are facilitated discussion among 8–12 carefully selected participants with similar backgrounds. Participants might be beneficiaries or program staff, for example. The facilitator uses a discussion guide. Note-takers record comments and observations.
Community group interview: These are a series of questions and facilitated discussion in a meeting open to all community members. The interviewer follows a carefully prepared questionnaire.

## Slide 20: Cont’s
Direct observation
Involves use of a detailed observation form to record what is seen and heard at a program site. The information may be about ongoing activities, processes, discussions, social interactions, and observable results.
Mini-survey
A structured questionnaire with a limited number of close ended questions that is administered to 50–75 people. Selection of respondents may be random or ‘purposive’ (interviewing stakeholders at locations such as a clinic for a health care survey).

## Slide 21: Participatory Methods
What are they?
Participatory methods provide active involvement in decision-making for those with a stake in a project, program, or strategy and generate a sense of ownership in the M&E results and recommendations.

## Slide 22: What can we use them for?
■ Learning about local conditions and local people’s perspectives and priorities to
design more responsive and sustainable interventions.
■ Identifying problems and trouble-shooting problems during implementation.
■ Evaluating a project, program, or policy.
■ Providing knowledge and skills to empower poor people.

## Slide 23: Advantages
■ Examines relevant issues by involving key players in the design process.
■ Establishes partnerships and local ownership of projects.
■ Enhances local learning, management capacity, and skills.
■ Provides timely, reliable information for management decision-making.
Disadvantages
■ Sometimes regarded as less objective.
■ Time-consuming if key stakeholders are involved in a meaningful way.
■ Potential for domination and misuse by some stakeholders to further their own interests.

## Slide 24: Commonly Used Participatory Tools
Stakeholder analysis: is the starting point of most participatory work and social assessments. It is used to develop an understanding of the power relationships, influence, and interests of the various people involved in an activity and to determine who should participate, and when.
Participatory rural appraisal: is a planning approach focused on sharing learning between local people, both urban and rural, and outsiders. It enables development managers and local people to assess and plan appropriate interventions collaboratively often using visual techniques so that non-literate people can participate.

## Slide 25
Beneficiary assessment: involves systematic consultation with project beneficiaries and other stakeholders to identify and design development initiatives, signal constraints to participation, and provide feedback to improve services and activities.
Participatory monitoring and evaluation: involves stakeholders at different levels working together to identify problems, collect and analyze information, and generate recommendations.

## Slide 26: Public Expenditure Tracking Surveys
What are they?
Public expenditure tracking surveys (PETS) track the flow of public funds and determine the extent to which resources actually reach the target groups.
The surveys examine the manner, quantity, and timing of releases of resources to different levels of government, particularly to the units responsible for the delivery of social services such as health and education.
PETS are often implemented as part of larger service delivery and facility surveys which focus on the quality of service, characteristics of the facilities, their management, incentive structures, etc.

## Slide 27
What can we use them for?
■ Diagnosing problems in service delivery quantitatively.
■ Providing evidence on delays, “leakage,” and corruption.
ADVANTAGES:
■ Supports the pursuit of accountability when little financial information is available.
■ Improves management by pinpointing bureaucratic bottlenecks in the flow of funds for service delivery.
DISADVANTAGES:
■ Government agencies may be reluctant to open their accounting books.
■ Cost is substantial.

## Slide 28: Cost-Benefit and Cost-Effectiveness Analysis
What are they?
Cost-benefit and cost-effectiveness analysis are tools for assessing whether or not the costs of an activity can be justified by the outcomes and impacts. Cost-benefit analysis measures both inputs and outputs in monetary terms. Cost-effectiveness analysis estimates inputs in monetary terms and outcomes in non-monetary quantitative terms (such as improvements in student reading scores).

## Slide 29
What can we use them for?
■ Informing decisions about the most efficient allocation of resources.
■ Identifying projects that offer the highest rate of return on investment.
ADVANTAGES:
■ Good quality approach for estimating the efficiency of programs and projects.
■ Makes explicit the economic assumptions that might otherwise remain implicit or overlooked at the design stage.
■ Useful for convincing policy-makers and funders that the benefits justify the activity.
DISADVANTAGES:
■ Fairly technical, requiring adequate financial and human resources available.
■ Requisite data for cost-benefit calculations may not be available, and projected results may be highly dependent on assumptions made.
■ Results must be interpreted with care, particularly in projects where benefits are difficult to quantify.

## Slide 30: Impact Evaluation
What is it?
Impact evaluation is the systematic identification of the effects positive or negative, intended or not on individual households, institutions, and the environment caused by a given development activity such as a program or project.
Impact evaluation helps us better understand the extent to which activities reach the poor and the magnitude of their effects on people’s welfare.
Impact evaluations can range from large scale sample surveys in which project populations and control groups are compared before and after, and possibly at several points during program intervention; to small-scale rapid assessment and participatory appraisals where estimates of impact are obtained from combining group interviews, key informants, case studies and available secondary data.

## Slide 31
What can we use it for?
■ Measuring outcomes and impacts of an activity and distinguishing these from the influence of other, external factors.
■ Helping to clarify whether costs for an activity are justified.
■ Informing decisions on whether to expand, modify or eliminate projects, programs or policies.
■ Drawing lessons for improving the design and management of future activities.
■ Comparing the effectiveness of alternative interventions.
■ Strengthening accountability for results.

## Slide 32
ADVANTAGES:
■ Provides estimates of the magnitude of outcomes and impacts for different demographic
groups, regions or over time.
■ Provides answers to some of the most central development questions – to what extent are we making a difference? What are the results on the ground? How can we do better?
■ Systematic analysis and rigor can give managers and policy-makers added confidence in decision-making.
DISADVANTAGES:
■ Some approaches are very expensive and time-consuming, although faster and more economical approaches are also used.
■ Reduced utility when decision-makers need information quickly.
■ Difficulties in identifying an appropriate counter-factual.

## Slide 33: 4 Models of Impact Evaluation
1. Randomized pre-test post-test evaluation.
2. Quasi-experimental design with before and after comparisons of project and control populations.
3. Ex-post comparison of project and non-equivalent control group.
4. Rapid assessment ex-post impact evaluations.

## Slide 34: Conclusion
It should be noted that there are a wide range of PM&E Tools and Methods. However its important to consider the type of Project so as to make the right choice.