## Slide 1: Establishing a Monitoring and Evaluation System

## Slide 2: Key terms
Monitoring
  Is the systematic collection and analysis of information as a project progresses.
Evaluation
  Is the comparison of actual project impacts against the agreed plan.

## Slide 3: What is a M & E system?
  A system of collecting and utilising information regarding the progress of the project or program.
  Also a means of collecting and communicating information on project progress.
  It is a systematic monitoring and evaluation plan.
The main purpose of M & E system is to:
  Facilitate learning within the project.
  Informed decision making within the project.
  Generating relevant timely information and making this available for project stakeholders (accountability).

## Slide 4: Objective of M & E System
The main objective for developing the M&E system is to facilitate learning and to inform decision making within the organisations.
The system is also aimed at generating relevant & timely information
The information should be made available for project stakeholders.
Improving project management and ensuring optimum use of funds and other resources.
Facilitate learning so as to improve the relevance and outcome of the programme.
Strengthening the capacity of the organisation and the community to monitor and evaluate their activities.
Meeting funders requirements to ensure resources are used effectively, efficiently and for agreed objective

## Slide 5: Purpose/Relevance of M & E System
The M & E system will serve to:
Improve the effectiveness & implementation of the project components by signaling when impact is less than anticipated and identifying possible problems.
Strengthen the organization's ability to report results and justify resource requests to the donors.
Identify lessons learned and best practices.
Ensure that all organizations' project funds are used effectively within the agreed frame and budget.
Ensure continuous learning and quality control for the organization’s programme.
Support the broader programme management requirement.

## Slide 6: Process of Designing M & E System
Define the aim/purpose of the M&E System
Baseline information
Select the relevant information
  Examine and refer to the project goal, objectives, activities and performance indicators.
  Identify what project components and issues that are to be monitored and evaluated
  Relevance; efficiency; effectiveness; outcomes; impact; replicability; sustainability.= Evaluation questions?
Design the M&E tools
Collect and analyze data
Present and use information

## Slide 7: Monitoring and Evaluation Plan
M& E is critical for keeping track of activities and resources.
M & E plan describes M&E objectives, strategies, methodologies, work plan, its activities in detail and the technical tools to be used
Key components/elements include:
  Key questions for monitoring
  Indicators
  Baseline data
  Frequency of data collection
  How information will be collected
  Who is involved
  How the information collected will be used

## Slide 8: M & E Plan answers the following questions
What indicators are being monitored and evaluated?
What information is needed to track the indicator?
What are the sources of the information?
What data collection methods are appropriate?
Who will collect the information?
How often will it be collected?
Who will receive and use the results?

## Slide 9: Monitoring & Evaluation Plan
Project elements | OVIs | MOV | Assumptions | Indicators | Info Needed | Sources of Data | Methods of Data Collection | Who Collects | Frequency of Collection | Users |  | 
Goal (Impact) |  |  |  |  |  |  |  |  |  |  |  | 
Purpose (Outcome) |  |  |  |  |  |  |  |  |  |  |  | 
Outputs |  |  |  |  |  |  |  |  |  |  |  | 
Activities |  |  |  |  |  |  |  |  |  |  |  | 
Inputs |  |  | Risks & Preconditions |  |  |  |  |  |  |  |  | 

## Slide 10: Developing Indicators for Monitoring and Evaluation
When developing indicators, the norm is to use SMART criteria to guide performance indicator conceptualization. SMART is an acronym with the following meaning:
Specific – What does the project intend to change?
Measureable – Can the indicator be assessed objectively and independently?
Achievable – Is it possible for the objective to accomplish the indicator?
Relevant – Is the indicator applicable to the context and the project as well as practical or cost-effective to use?
Time-bound – By when will the indicator be achieved? Can the indicator be achieved when it is required?

## Slide 11: Key Documents Required for M&E System
The following are key for each project
  Needs Assessment/ situational analysis report
  The project implementation manual;
  Final results framework
  Project monitoring and evaluation plan
  Monthly/Quarterly/Weekly performance progress reports

## Slide 12: Standard Criteria for Assessing the Quality of Your M&E System
Utility
  The M&E system will serve the practical information needs of intended users;
Feasibility
  The methods, sequences, timing and processing procedures proposed are realistic, prudent and cost effective;
Propriety
  The M&E activities will be conducted legally, ethically and with due regard for the welfare of those affected by its results;
Accuracy
  The M&E outputs will r