## Slide 1: Project Organization
Project structure; Functional. Projectized and Matrix Structures
Project Manager and Project Management Skills
Project management processes groups
Project management knowledge areas
Project Management Key documents
Project Charter
Project management plan
Work breakdown Structure
scope statement

## Slide 2: Project Organization
What is project organization?

## Slide 3: Project Organization, cont.
Project organization refers to how resources, roles, and processes are structured and coordinated to ensure the successful completion of a project.
It defines how people, tasks, and responsibilities are arranged to achieve project objectives efficiently.

## Slide 4: Project structure
what is a project structure?
A project structure refers to how a project is organized in terms of its components, such as files, folders, resources, and workflows.
A well-organized project structure makes development, collaboration, and maintenance easier.
The structure depends on the type of project (e.g., software system, or academic project), the team, and the tools or frameworks used.

## Slide 5: General Elements of a Project Structure
Project Scope: Includes the objectives, deliverables, and boundaries.
Key Components: Defines the main parts of the project (e.g., code, documentation, assets, etc.)
Workflow: The process and tools for managing tasks and changes.
Dependencies: External libraries, frameworks, or tools required.

## Slide 6: Why is Project Structure Important?
Clarity: Ensures everyone knows where to find files.
Scalability: It is easier to add new features or files without creating clutter.
Collaboration: Teams can work together efficiently.
Maintenance: Bugs and updates are easier to handle with a logical structure.
Enhances accountability
Better resoutce mgt: allocate money,time, materials,H/R

## Slide 7: Types of Project Structures
Majorly 3
Functional Structure
Description: The project is organized within the existing functional departments (e.g., Marketing, IT, finance).

## Slide 8: Key Features of functional structure
Team members report to department heads.
The project manager has limited authority.
Tasks are handled by the respective functional units.

## Slide 9: Types of Project Structures-cont.
2. Projectized Structure
Is where the project manager has full authority and the team works only on that specific project.
Description: The project team is fully dedicated to the project, and the project manager has full authority.

## Slide 10: Types of Project Structures-cont.
Key Features:
Team members report directly to the project manager.
Focused and centralized decision-making.
Full authority of the project manager
Resource control within the project
Temporary structure

## Slide 11: Merits & demerits of Projectized Structure
Advantages | Disadvantages
Clear authority and accountability. | High resource cost (dedicated staff).
Team is fully committed to the project. | Risk of resource redundancy once the project ends.
Fast decision-making and adaptability. | Best for: Large, high-priority projects requiring dedicated focus.

## Slide 12: Types of Project Structures-cont.
3. Matrix Structure
Description: Combines elements of both functional and projectized structures, where team members report to both the functional manager and the project manager.

## Slide 13: Types of Project Structures-cont.
Key Features of Matrix Structure:
Shared authority between functional and project managers.
Resources are used across projects and departments.
improved communication across departments
Potential for conflict

## Slide 14: Types of Project Structures-cont
Types of Matrix Structures:
Weak Matrix: Functional managers have more authority than project managers.
Balanced Matrix: Authority is equally shared between functional and project managers.
Strong Matrix: Project managers have more authority than functional managers.

## Slide 15: Project Manager
What/who is a project manager?

## Slide 16: Project Manager-cont.
A Project Manager (PM) is a professional responsible for leading a project from initiation to completion.
They oversee planning, resource allocation, execution, and monitoring to ensure the project is delivered on time, within budget, and meets its objectives.
The PM is the key point of contact between stakeholders, the project team, and the organization.

## Slide 17: Key Roles and Responsibilities of a Project Manager
Project Planning and Scheduling
Define project scope, goals, and deliverables.
Develop detailed project plans, schedules, and milestones.
Identify dependencies and critical paths.
Resource Management
Allocate resources (human, financial, material) efficiently.
Identify skills needed and form a cohesive project team.
Manage external vendors or contractors, if applicable.
Risk and Issue Management
Identify potential risks and develop mitigation plans.
Address issues promptly to minimize project disruption.

## Slide 18: Key Roles and Responsibilities of a Project Manager-cont.
Leadership and Team Management (Motivate and guide the project team toward success, resolve conflicts)
Stakeholder Communication (bridge between stakeholders and the team, Provide regular updates and manage expectations)
Budget Management (Plan, monitor, and control the project budget).
Monitoring and Reporting (Use metrics and KPIs to measure project performance). Generate status reports and identify areas for improvement).
Project Closure (Ensure deliverables meet quality standards and are signed off, Conduct lessons-learned sessions for future improvements, Archive documentation and officially close the project.

## Slide 19: Project management processes groups
The project management process groups are fundamental phases in the lifecycle of a project as defined by the Project Management Institute (PMI) in the PMBOK (Project Management Body of Knowledge). Five groups outline the logical progression of a project from start to finish and ensure that all aspects are planned, executed, monitored, and completed efficiently.

## Slide 20: Project management processes groups-cont.
1. Initiating Process Group
Purpose: To define and authorize the project or phase.
Key Activities:
  Define the project’s purpose, objectives, and scope.
  Identify stakeholders and determine their expectations.
  Develop a Project Charter (officially authorizes the project).
  Identify high-level risks and constraints.
Key Outputs: Project Charter &Stakeholder Register

## Slide 21: Project management processes groups-cont
2. Planning Process Group
Purpose: To establish the project’s roadmap for achieving its objectives.
Key Activities:
  Develop the Project Management Plan (comprehensive plan for execution, monitoring, and closure).
  Define project scope, schedule, budget, quality standards, and resources.
  Identify risks and develop mitigation strategies.
  Plan communications and stakeholder engagement.
Key Outputs: Project Management Plan
Work Breakdown Structure (WBS)
Risk Management Plan
Schedule and Budget Baselines

## Slide 22: Project management processes groups-cont
3. Executing Process Group
Purpose: To complete the work defined in the project plan and deliver the desired results.
Key Activities:
  Direct and manage project work.
  Acquire, develop, and manage the project team.
  Conduct procurement activities and manage vendor relationships.
  Ensure stakeholder engagement and communicate project progress.
Key Outputs:
  Deliverables, Work Performance Data, Updates to the Project Plan

## Slide 23: Project management processes groups-cont
4. Monitoring and Controlling Process Group
Purpose: To track, review, and regulate project progress and performance.
Key Activities:
  Monitor project performance using key performance indicators (KPIs).
  Control scope, schedule, cost, and quality to ensure the project stays on track.
  Identify and address variances from the plan.
  Perform integrated change control (evaluate and approve/reject changes).
Key Outputs:
  Work Performance Reports
  Change Requests
  Updates to the Project Plan

## Slide 24: Project management processes groups-cont
5. Closing Process Group
Purpose: To finalize the project, deliver its outcomes, and formally close it.
Key Activities:
  Confirm deliverables meet quality standards and gain stakeholder approval.
  Release project resources (e.g., team, budget).
  Document lessons learned for future projects.
  Close contracts with vendors or suppliers.
Key Outputs:
  Final Deliverables
  Project Closure Report, Lessons Learned Document

## Slide 25: Project management knowledge areas
Knowledge Area | Key Process Groups | Output
Integration Management | All five groups (Initiating to Closing). | Project Charter, Project Management Plan, Change Log, Project Closure Report.
Scope Management | Initiating, Planning, Monitoring and Controlling. | Scope Statement, Requirements Documentation, WBS, Change Requests.
Schedule Management | Planning, Monitoring and Controlling. | Project Schedule, Schedule Baseline, Gantt Charts.
Cost Management | Planning, Monitoring and Controlling. | Cost Baseline, Budget Forecasts, Cost Performance Reports.
Quality Management | Planning, Executing, Monitoring and Controlling. | Quality Management Plan, Quality Metrics, Quality Reports.

## Slide 26: Project management knowledge areas-cont.
Resource Management | Planning, Executing, Monitoring and Controlling. | Resource Management Plan, Team Assignments, Resource Utilization Reports.
Communications Management | Planning, Executing, Monitoring and Controlling. | Communication Plan, Performance Reports, Stakeholder Updates.
Risk Management | Planning, Monitoring and Controlling. | Risk Register, Risk Response Plans, Risk Monitoring Updates.
Procurement Management | Planning, Executing, Closing. | Procurèrent Management Plan, Contracts, Procurèrent Reports.
Stakeholder Management | Initiating, Planning, Executing, Monitoring and Controlling. | Stakeholder Register, Stakeholder Engagement Plan, Engagement Reports.

## Slide 27: Project Management Key documents
Document | Purpose
Project Charter | Defines the project’s purpose, objectives, stakeholders, and high-level requirements. Officially authorizes the project. Includes initial risks, constraints, and project approval.
Project Management Plan | Comprehensive document outlining how the project will be executed, monitored, controlled, and closed. Includes subsidiary plans like the scope, schedule, cost, quality, and resource management plans.
Work Breakdown Structure (WBS) | Hierarchical breakdown of project tasks and deliverables. Helps in organizing and defining the total scope of the project.
Scope statement | clearly defines what is included and what is excluded forms the basis for scope verification and control

## Slide 28: other project mgt documents
project schedule
Risk register
stakeholder register
lessons

## Slide 29: CONCLUSION
Project organization is a critical component of project management that determines how teams, resources, and responsibilities are structured to achieve project goals effectively. So choosing an appropriate organizational matrix team can optimize collaboration, accountability, and resource utilization.

## Slide 30: END
THANK YOU