## Slide 1: Project Monitoring & Evaluation
By Francis Kenneth Kimbugwe

## Slide 2
Notes: Even projects with exceptional planning, optimal resources and rigorous implementation will not automatically achieve their desired results. Throughout the project life cycle, challenges/problems/issues will arise and it is the responsibility of the project manager to keep control of the project to the end. Fortunately, there are indispensible tools that assist the project manager’s efforts to ensure that the project are tracked, measured and controlled.
These tools can generally be organized into four categories:
Project Monitoring: Constantly checking to ensure that the implementation is progressing as planned.
Project Evaluation: Assessing whether the expected benefits will be delivered and are still valid.
Project Risk Management: Actively identifying and managing project risks that may influence the capacity of the project to achieve its results for the end population to take advantage of the project benefits.
Integrated Change Management: Ensuring that all proposed project changes (scope, budget, schedule, quality, procurement, monitoring and evaluation, procurement, transition, etc.) are assessed and logged, and appropriate action is taken.

## Slide 3: Project Mgt

## Slide 4: Looking as a process
Series of actions or activities processes, to generate a deliverable.
Input(resources) Outputs – Outcomes - Impact.
Activities
XXXX ++++

## Slide 5: A project
A project is a temporary endeavor undertaken to create a unique product, service, or result.
  Unique product, service, or result. Projects are undertaken to fulfill objectives by producing deliverables.
  Temporary endeavor. The temporary nature of projects indicates that a project has a definite beginning and end.
  Projects drive change. Projects drive change in organizations.

## Slide 6
  Projects enable business value creation. PMI defines business value as the net quantifiable benefit derived from a business endeavor.
  Project Initiation Context. Organizational leaders initiate projects in response to factors acting upon their organizations.
  Elaborative progression - PLC

## Slide 7: When is a project end reached?
The project’s objectives have been achieved
The objectives will not or cannot be met
Funding is exhausted or no longer available for allocation to the project.
The need for the project no longer exists (e.g., the customer no longer wants the project completed, a change in strategy or priority ends the project, the organizational management provides direction to end the project).
The human or physical resources are no longer available.
The project is terminated for legal cause or convenience.

## Slide 8
Project monitoring can be important for many stakeholders, including project funders, as it ensures that similar programs be replicated elsewhere, as seen in other financial sector operations that focus on a few locations (Marangu, 2012).
Monitoring is the process of tracking, assessing, and regulating development in order to meet the performance objectives specified in the project management plan.
Monitoring involves establishing indicators, implementing data collection techniques, collecting, documenting, and analyzing data, and using the data to inform daily project management.
Monitoring is essential because it compels activities to be modified if they fail to produce the desired project performance, claim Karanja &Muchelul (2018).

## Slide 9: By the end of this lecture participant should be able to;
Define & distinguish project monitoring, evaluation and control.
Justify project monitoring, evaluation and control during implementation of a project.
Different question asked during M&E
Different forms of Project Evaluation.
Identify the criteria for successful project evaluation
Benefits of M&E

## Slide 10: Indispensable tools
Project Monitoring
Project Evaluation
Project Risk Management
Integrated Change Management

## Slide 11: Points to remember!
Monitoring activities primarily correspond to the two lower levels of the project logical framework (activities & outputs) and inputs required to execute the activities.
Evaluation activities primarily correspond with the two upper levels of the project logical framework (Outcomes & Goals). However, it may review progress at the first two level.

## Slide 12: Differentiating between Project Monitoring and Project Evaluation
Criteria | Monitoring | Evaluation
WHAT |  | 
WHY |  | 
HOW |  | 
WHO |  | 
WHEN |  | 

## Slide 13: Overview
Planning a project well is not and ends in itself.
A project manager must therefore permit monitoring, evaluation and control of operations.
Monitoring, Evaluation and Control processes continually compare actual performance to the project implementation plan (variance analysis).
  When variance is found, the project teams need to analyze the cause of the variance,
  identify potential corrective actions, and
  implement changes to realign the model (project implementation plan) with the reality of the project context.

## Slide 14: Illustration of Log frame
Narrative summary/Intervention logic/project elements | OVIs | MOVs/SOVs | Assumptions
Project Goal(Impact) |  |  | 
Project Purpose/major Objective (Outcome) |  |  | 
Project outputs (objectives) |  |  | 
Project activities | Inputs/ Resources | Costs | Risks & Preconditions

## Slide 15: Overview cont’d
Tools and procedures for performing these three factors must be designed and established at concept stage.
The indispensible tools that assist the project manager’s efforts to ensure that the project are tracked, measured and controlled can be categorized as;
Project Monitoring
Project Evaluation:
Project Risk Management
Integrated Change Management (Control)

## Slide 16: Project monitoring
Monitoring is the process of observing progress and resource utilization, and anticipating deviations from planned performance/ expectations.
  Monitoring is carried out by project staff and it is the responsibility of the project’s management to ensure that it takes place and is used to inform how the project is managed.
  Its purpose is to bring to the attention of projects staff to any changes relevant to project implementation. They can then decided how best to respond to these changes.
Note: As an essential aspect of good management practice, monitoring takes place throughout the entire period of the project life

## Slide 17: Questions monitoring addresses during PI
How are the resources being used?
What progress is being made?
Are the results of the project's work being used by the target group?
Are there any important changes in the project's context?
Which Activities are underway and what progress has been made (e.g. at weekly intervals)?

## Slide 18: Questions monitoring addresses during PI
At what rate are means being used and cost incurred in relation to progress in implementation (e.g. monthly)?
Are the desired Results being achieved (e.g. quarterly update)? (efficiency)
To what extent are these Results furthering the Project Purpose (e.g. half-yearly analysis)? (effectiveness)
What changes in the project environment occur? Do the Assumptions hold true?

## Slide 19: Why monitoring during project implementation?
To determine the real start and or finish dates for each task.
To assess the actual work done by internal resources during regular hours and overtime.
Determination of actual internal costs.
Determination of external cost contributions.
Verification of performance indicators, set for project objectives during planning and design stage.

## Slide 20: Benefits of Project Monitoring
Allows mgt to give visible consistent feed back to internal and external stakeholders.
Stimulates translation of objectives into visible performance standards.
It assures that standards are realistic, fair and that they remain so overtime.
Allows measurement of consumed resources in the project.
It helps us to learn from our experiences, and to improve how we do things.
Monitoring helps us to manage the work.
It can draw out attention to important signs about how our work is progressing, and can inform us about significant changes in which we are carrying out this work.

## Slide 21: Foundations of monitoring
A sound framework for project monitoring.
Positive organisational culture.
Appropriate organisational structure, procedures and policies.
Effective information management.
Skilled staff.
Resource availability

## Slide 22: Project Evaluation
An assessment of performance at a particular point of project implementation.
It is concerned with what happens once a project has been put into operation/during its implementation.
A process of judging value on what a project or programme has achieved particularly in relation to activities planned and overall objectives.

## Slide 23: Project Purpose: To improve infant mortality Rate
Target Group: A group used as a vehicle to bring about the desired change. That group whose behavior the project should target to change in order to bring about the desired change. Received the products/service delivered by the project.
  Expecting mothers
  Care givers
  Hospitals staff
Beneficiaries: A groups that receive the final benefits or deliverables to the project.
  Babies below 5
  Parents

## Slide 24: Evaluation Forms
An evaluation can be done;
  Before implementation (Exante evaluation)
  during implementation (mid-term),
  at its end (final evaluation) or
  afterwards (expost evaluation),
  either to help guide the project or to draw lessons for future projects and programming.

## Slide 25: Evaluation Forms cont’d
Looking at what the project or organisation intended to achieve – what difference did it want to make? What impact did it want to make?
Assessing its progress towards what it was to achieve, its impact targets.
Looking at the strategy of the project or organisation. Did it have a strategy? Was it effective in following its strategy? Did the strategy work? If not, why not?

## Slide 26: Evaluation Forms cont’d
Looking at how it worked.
Was there an efficient use of resources?
What were the opportunity costs of the way it chose to work?
How sustainable is the way in which the project or organisation works?
What are the implications for the various stakeholders in the way the organisation works?

## Slide 27: Stages of Project Evaluation
Two kinds or stages are popularly talked about in literature.i.e.
Formative evaluation, and
Summative evaluation.
Illustration:
When the cook tastes the soup. What is that?
When the guests taste the soup. What is that?

## Slide 28
Project Evaluation
Formative Evaluation
Summative Evaluation

## Slide 29: Formative evaluation
Formative evaluation begins during project development and continues throughout the life of the project.
The purpose of a formative evaluation is to assess initial and ongoing project activities.
when the project is still under way: such interim evaluation are usually under-taken at mid-term (mid-term evaluation), to review progress and propose alterations to project design during the remaining period of implementation.
Formative evaluation has two components. i.e. implementation evaluation and progress evaluation.

## Slide 30: Results Chain/TOC
Inputs
Outputs
Activities
Outcomes
Impact

## Slide 31: 1. Implementation evaluation
The purpose of implementation evaluation is to assess whether the project is being conducted as planned.
This type of evaluation, sometimes called “process evaluation,” may occur once or several times during the life of the project/program.
The underlying principle is that before you can evaluate the outcomes or impact of a program, you must make sure the project and its components are really operating and, if they, are operating according to the proposed plan or PIP.

## Slide 32: 2. Progress Evaluation
The purpose of a progress evaluation is to assess progress in meeting the goals of the program and the project.
Progress evaluation collects information to determine what the impact of the activities and strategies is on participants at various stages of the intervention.
By measuring progress, project staff can eliminate the risk of waiting until participants have experienced the entire project to assess likely outcomes.
Note: Progress evaluation is useful throughout the life of the project, but is most vital during the early stages when activities are piloted and their individual effectiveness or articulation with other project components is unknown.

## Slide 33: Summative evaluation.
Sometimes referred to as impact or outcome evaluation.
The purpose of a summative evaluation is to assess the quality and impact of a fully implemented project.
Assesses a mature project’s success in reaching its stated goals. It can be carried out at:
At the end of a project to document the resources used, results and progress towards objectives.
The objective is to generate lessons about the project which can be used to improve future designs.
2. A number of years after completion (ex post evaluation), often focusing on impact.
Summative evaluation collects information about outcomes and related processes, strategies, and activities that have led to them.

## Slide 34: Key questions
To what extent does the project meet the stated goals for change or impact?
Are there any impacts on the participants ?
Are there any changes taking place?
Which components are the most effective?
Which components are in need of improvement?
Were the results worth the project’s cost?
Can the project be sustained?
Is the program replicable and transportable?

## Slide 35: Other types of Evaluation
Evaluation can be classified in terms of timing, scope, and agent.
By timing: Mid term Evaluation, Terminal evaluation, Ex-post evaluation.
By scope: Project /programme evaluation, Sectoral evaluation, Thematic evaluation.
By agent: Internal or self evaluation, External evaluation or Joint evaluation.
Notes: Based on when they are conducted: Ex-ante evaluation: An ex-ante evaluation is made to assess the potential impact of a project, program or policy intervention before implementation. Ex-ante evaluation is a process that supports the preparation of proposals for new interventions. Its purpose is to gather information and carry out analyses that help to ensure that the objectives can be met and that the method used is cost-effective. It is done to estimate costs and benefits and assesses the potential impact of an intervention before it is implemented. Ex-ante evaluations are done by peer or expert reviews using checklists, scoring models, or cost–benefit analysis. Ex-ante evaluation can provide an idea of what range of impact to expect after the project/program/ policy is implemented. It can also assist in setting up an appropriate M&E system for ex-post impact assessment. Moreover ex-ante evaluation methods can be used to identify how the impacts would change if some parameters of the program were changed. Ex-ante evaluation is a tool for improving
the quality of new or renewed projects/programs and for providing information on the basis of which decision-makers can judge the value of a proposal. Therefore, it is important to start ex-ante evaluation work early on in the process when options for project/program formulation are still open. Ongoing evaluation: Ongoing evaluations review ongoing activities to provide guides for corrective implementation measures in order to achieve intended results better. As such, ongoing evaluation is conducted during the implementation stage. Periodic evaluation of ongoing interventions is conducted to analyse the use of resources, the quality of work, and the continuing relevance of the intervention. It is also used to review implementation progress and predict likely effects of interventions and highlight necessary adjustments in work design. Mid-term evaluation which is conducted at the middle of a project/program life, serve as a means of validating the results of initial assessments obtained from monitoring activities. Ongoing evaluations address problems associated with the day-to-day management of interventions and also can indicate the need for changes in project, program or policy objectives and targets. Ex-post evaluation: An ex-post evaluation assesses the interventions performance, quality, relevance, efficiency and impact immediately after implementation is completed. An ex-post evaluation is linked to an ex-ante evaluation, and is best conducted where a baseline has been originally defined, targets have been projected, and data has been collected on important indicators. Information collected through monitoring is also fundamental for the success of ex-post evaluation. This kind of evaluation provides an overall assessment of the intervention’s performance, cost effectiveness, its relevance to development goals, and acceptance of the results by end users and/ or its impacts. Ex-post evaluation also assesses the extent to which an intervention has succeeded in meeting its objectives. Moreover, in addition to providing information about potential sustainability of an intervention, ex-post evaluation helps to obtain feedback from the target group. Most of the time ex post evaluation is carried out through participatory meetings at the site with peers, farmers, extension staff, NGOs and other relevant stakeholders. Impact evaluation is a form of ex-post evaluation and attempts to determine the extent to which the intervention has contributed to the achievement of the larger development goal (see next section for more on impact evaluation)
Based on agent
Internal evaluation In internal evaluation, sometimes called self-evaluation, a unit and/or individuals reporting to the management of the donor, partner or implementing organization conduct the evaluation. The advantage of using internal evaluator is that insiders know the organization and therefore may be able to interpret the results better than an external body. The disadvantage of using internal evaluator is that internal evaluator may avoid negative conclusions. In other words, strengths and weaknesses might not be interpreted fairly when data and results are analysed by internal staff members. External evaluation This is a type of evaluation in which the evaluation of a development intervention is conducted by entities and/or individuals outside the implementing or donor agency. Many organizations may not have the resources to carry out the ideal evaluation. In such cases external evaluation consultant is recruited to lead the evaluation process. An external evaluator may be more objective, free from organizational bias and may contribute fresh perspectives. Joint evaluation In joint evaluation different implementing and donor agencies as well as partners participate in the evaluation. The degree of ‘jointness’ may vary depending on the extent to which individual partners cooperate in the evaluation process, contribute resources for the evaluation and combine their evaluation reporting. Joint evaluation can help overcome the problem of attribution problems in assessing the effectiveness of programs and strategies and the complementarity of efforts supported by different partners etc.
Based on the types of questions they are expected to answer Different types of evaluations are required for different types of questions. It is important for decision makers to know what type of evaluative information they need to have. Performance logic chain assessment evaluation The performance logic chain assessment evaluation is used to evaluate the strength and logic of the causal model underlying the project/program/policy. The causal model addresses the deployment and sequencing of the resources, activities or policy strategies that can be used to achieve a desired change in an existing situation. The purpose of a performance logic chain assessment evaluation is to avoid failure from a weak or inappropriate design of an intervention. Pre-implementation assessment evaluation

## Slide 36: Based on the types of questions they are expected to answer
Performance logic chain assessment evaluation
  used to evaluate the strength and logic of the causal model underlying the project/program/policy.
  The causal model addresses the deployment and sequencing of the resources, activities or policy strategies that can be used to achieve a desired change in an existing situation.
  The purpose of a performance logic chain assessment evaluation is to avoid failure from a weak or inappropriate design of an intervention.

## Slide 37: Based on the types of questions they are expected to answer
Pre-implementation assessment evaluation.
Conducted just before the implementation phase.
The pre-implementation assessment evaluation attempts to answer three fundamental questions that underlie an intervention:
  Are the objectives well defined so that outcomes can be stated in measurable terms?
  Is there a coherent and credible implementation plan that provides clear evidence of how implementation is to proceed, and how successful implementation can be distinguished from poor implementation.
  Is the rationale for the deployment of resources clear and commensurate with the requirements for achieving the stated outcomes?
The purpose of such evaluation is to ensure that failure is not programmed in from the beginning of implementation

## Slide 38: Based on the types of questions they are expected to answer
Process implementation evaluation
Focus on the intervention itself, i.e. its operation, activities, functions, performance, component parts, resources etc.
Involves assessment of the performance of an intervention with regard to service utilization and organization of the intervention.
Specifically it attempts to answer questions such as:
  What did or did not get implemented that were planned?
  What congruence was there between what was intended to be implemented and what actually happened?
  How appropriate and close to plan were the costs; the time requirements; the staffing capacity, and capability; the availability of required f inancial resources, facilities and staff; and political support?
Notes:   Assessing service utilization consists of examining the extent to which the intended target population receives the intended services.
  On the other hand assessing the organization of the intervention requires comparing the plan for what the intervention should be doing with what is actually done, especially with regard to providing services.

## Slide 39: Based on the types of questions they are expected to answer
  What unanticipated and unintended outputs or outcomes emerged from the implementation phase?
  Whether the intervention is reaching the target population (e.g. how many persons are receiving services? Are the intended targets receiving proper amount, type, and quality of services, are the target population aware of the project/program

## Slide 40: Based on the types of questions they are expected to answer
Impact evaluation
conducted some time after the completion of an intervention and their objective is to determine the effect of interventions on beneficiaries.
Impact evaluation goes beyond the direct result of an intervention and tries to study the effects of the intervention on the ultimate users.

## Slide 41: Based on the types of questions they are expected to answer
Meta evaluation
Evaluations designed to aggregate findings from different evaluations
Given a number of evaluations that are available on one or similar interventions, a meta-evaluation is used to establish the criteria and procedures for systematically looking across those existing evaluations to summarize trends and to generate confidence (or caution) in the cross-study f indings.
Meta evaluations attempt to answer questions like ‘what do we know at present on this issue and what is the level of confidence with which we know?’
Meta evaluations are quick way of learning from previously conducted evaluations.

## Slide 42: Major Principles of Evaluation
Impartiality & independence.
Credibility depending on expertise and independence of the evaluators.
Usefulness- relevant, presented in a clear and concise way, reflecting the interests and needs of the parties involved, easily accessible, timely and at the right moment.
Participation of stakeholders.

## Slide 43: In order to get the best out of project evaluation
It should be carried out by an external a private party preferably external.
The external party should be qualified and with no vested interests whether directly and indirectly.
The TOR (Terms of Reference) must be exhausted, incorporating materials for involvement, specifics for emphasis and the need for recommendation.
Management has to be willing and ready to facility the exercise.
Management should also arrange interviews with other relevant parties and budget for logistical support to this cause.
The exercise must be executed in a timely and effective manner, since many activities of the project tend to be withheld until after the outcome of the project evaluation.

## Slide 44: Reference Material
Development Projects Observed by Hirsman (1967).

## Slide 45: Benefits of Project Evaluation
Class discussion
What is the foundations for project monitoring in an organization?
What are the benefits of Project Evaluation during implementation of a Project?
3. What is the difference between Monitoring, Evaluation, Control and Audit?

## Slide 46: Thank you

## Slide 47: COURSE WORK ASSIGNMENT FOR MOINTORING AND EVALUATION Submission date:…………SEPTEMBER 2026
Describe each of the following monitoring and Evaluation tools and show how it works and its benefits in M & E.
  Theory of Change
  Logframe
  Performance Indicators,
  Rapid appraisal methods
  Impact evaluation
  Results-Based M & E
  Theory-based evaluation
  Formal surveys