## Slide 1: Establishing a Monitoring and Evaluation System `
By
Francis K.Kimbugwe

## Slide 2: Session Content
Meaning of a M &E System
Objective of developing an M &E System
Relevance of the M & E system
M & E Process
Tasks undertaken when developing M& E Plan
Key Project areas that are monitored.

## Slide 3: Key terms
Monitoring
  Is the systematic collection and analysis of information as a project progresses.
Evaluation
  Is the comparison of actual project impacts against the agreed plan.

## Slide 4: What is a M & E system?
  A system of collecting and utilizing information regarding the progress of the project or program.
  Also a means of collecting and communicating information on project progress.
  It is a systematic monitoring and evaluation plan.
The main purpose of M & E system is to:
  Facilitate learning and informed decision making with in the project.
  The system is also aimed at generating relevant timely information and making this available for project stakeholders.

## Slide 5: Objective of M & E System
The main objective for developing the M&E system is to facilitate learning and to inform decision making within the organisations.
The system is also aimed at generating relevant & timely information
The information should be made available for project stakeholders.
Improving project management and ensuring optimum use of funds and other resources.
Facilitate learning so as to improve the relevance and outcome of the programme.

## Slide 6: Objectives of M & E system cont’
Strengthening the capacity of the organisation and the community to monitor and evaluate their activities.
Meeting funders requirements to ensure resources are used effectively, efficiently and for agreed objectives.

## Slide 7: Purpose/Relevance of M & E System
The M & E system will serve to:
Improve the effectiveness & implementation of the project components
  By signaling when impact is less than anticipated and identifying possible problems.
Strengthen the organization's ability to report results and justify resource requests to the donors.
Identify lessons learned and best practices.
Ensure that all organizations' project funds are used effectively within the agreed time frame and budget.
Ensure continuous learning and quality control for the organization’s programme.
Support the broader programme management requirement.

## Slide 8: Process of Designing M & E System
Define the aim/purpose of the M&E System
Baseline information:
3. Select the relevant information
  Examine and refer to the project goal, objectives, activities and performance indicators.
  Identify what project components and issues that are to be monitored and evaluated
  Relevance; efficiency; effectiveness; outcomes; impact; sustainability; replicability.= Evaluation questions/ Parameters.
4. Design the M&E tools
  Good form design facilitate accurate recording of information
  Clear instructions
  Forms should contain enough information
  Ease of use of the form
5. Collect and analyze data
  Collection
  Data – when will data be collected- How will be collected- who collects-who reports
  Methods of collecting data: surveys with preset questionnaire; participatory methods; supervision and checklists,; Project visits; case studies; Regular record keeping/forms diaries.
  Recording manner
  Formats of project reporting
  Training and support.
  Analysis:
  Accuracy; Relevance ; People using the finding; results are available when needed. Who will evaluate the monitoring data; what will be the unit of analysis.
  Reflection
6. Present and use information :
  Communicating and reporting: Reporting schedule; Who receives the report and when; report the M& E findings to different stakeholders for difference.

## Slide 9: Step 1: Define the aim/purpose of the M&E System
1. Who needs the information and for what?
Information could be needed for:
  Accountability to donors and your own organization, partners, those affected by your work
  Day-to-day decision about your work
2. Set the objectives of the system.
Purpose evaluation Question: The core purposes of the M &E system for ….. is to provide the information needed for results-based management and to involve key stakeholder in learning how to improve project implementation.

## Slide 10: Step 2. Baseline Information/ Survey
These are studies that are carried out to establish a starting point for the project making it possible to see if anything has changed as a result of the project.
In project management, a baseline is a known state by which something is measured or compared.
Baseline is best established before a program is implemented.
Documenting the status is a vital component in project implementation process.

## Slide 11: Step3: Select the relevant information
1. Determine the information to be collected on the issues for monitoring.
VIP Construction: Information shall need to be collected?
Depth of the pit, Ventilation, Number of door, quality of materials used, size of the rooms, width and height of the walls, material mix etc. PDM project: Income earned after receiving PDM funds, household incomes, enterprise establishment/expansion, increased production, employment creation, improved household welfare, increased household assets, saving and investment, Food security, poverty reduction.
2. Decide what information will you will use.
3. Existing systems.
4. Identify the M&E questions and key indicators.
5. Set performance measurement question. How has the income levels of the PDM target households changed as compared to the non-target households? To what extent……

## Slide 12
We have implemented a project to construct VIPs around the two divisions of Arua City. As an M & E expert or project manager, what information will be collected about the VIP construction?
1.
2.
3.

## Slide 13: Monitoring and Evaluation Plan
Is critical for keeping track of activities and resources.
Describes M&E objectives, strategies, methodologies, work plan, its activities in detail and the technical tools to be used
  Key questions for monitoring
  Indicators
  Baseline data
  Frequency of data collection
  How information will be collected
  Who is involved
  How the information collected will be used

## Slide 14: Logical framework to monitor & Evaluation tool
Project Summary/intervention logic | OVIs | MOVs | Assumptions | Baseline | Frequency | Methods | Participants | Information | Use of Information |  | 
Project Goal: (Impact) Rural households in Kabale increase their average household income by 25% | % of families who produce enough food to cover lean periods. |  | - | 20% |  |  |  |  | Accountability/Learning/ Decision making |  | 
Project Purpose: (Outcomes) Subsistence farmers increase their crop yields by implementing more appropriate crop production methods | % of families adopting improved techniques | Where? How? -Review records of Extension workers. - Observe through site visits. |  |  |  |  |  |  |  |  | 
Project outputs: The Farmers’ Association is supported and strengthened in the target area. Farmers’ Groups Created. Modern Farming equipments distributed. | No. of farmers groups created. |  |  |  |  |  |  |  |  |  | 
Project activities 1.1 1.2 2.1 2.2 | Inputs |  | The System is stable |  |  |  |  |  |  |  | 

## Slide 15
Status |  | Frequency /When | Method |  |  |  |  | 
Baseline | Current |  | Quantitative | Qualitative |  |  |  | 
Impact: |  |  |  |  |  |  |  | 
20% | 60% | Weekly, Monthly, Quarterly /annaul | Surveys/Questionnaire | Interviews/Observation/ Story telling/document review. |  |  |  | 

## Slide 16: 2. Farmers’ Groups Created. (Output)
Activities:
2.1 Identifying farmers
2.2 Profiling farmers
2.3 Validating farmers
2.4 e.t.c
Inputs/Resources
2.1.1 Local council leaders.
2.1.2 Farmers’ lists.

## Slide 17: M & E Plan
Questions | Indicators | Baseline | Frequency | Methods | Participants | Information |  | 

## Slide 18: Key Documents Required for M&E System
The following are key for each project
  Needs Assessment/ situational analysis report
  The project implementation manual;
  Final results framework
  Project monitoring and evaluation plan
  Monthly/Quarterly/Weekly performance progress reports

## Slide 19: Quality of your M&E and Keeping It Updated
Once you have a detailed M&E system, two more steps are needed.
  First, you need to check the overall quality of the system itself, as designed.
    Second, you need to keep updating it to accommodate changing  information needs,
    skill levels and contexts as well as the
    refinements in project strategies and activities.

## Slide 20: Standard Criteria for Assessing the Quality of Your M&E System
Utility
  The M&E system will serve the practical information needs of intended users;
Feasibility
  The methods, sequences, timing and processing procedures proposed are realistic, prudent and cost effective;
Propriety
  The M&E activities will be conducted legally, ethically and with due regard for the welfare of those affected by its results;
Accuracy
  The M&E outputs will r

## Slide 21: Summary
What is going to be M&E? What methodologies are going to be used?
Who is going to M&E?
How will this data be evaluated?
What will be done with the M&E results